## Index (EN)
CEYLON SHIPPING CORPORATION LTD.
MV CEYLON PRINCESS
DRY DOCK SPECIFICATION - 2ND RENEWAL DRY DOCK REPAIRS
ENGINE ROOM REPAIRS (EN)
Job No | Description
CP/DD2/EN/001 | All sea suction and overboard valves.
CP/DD2/EN/002 | Boiler internal and external inspection and survey
CP/DD2/EN/003 | Main engine all units main bearings, cross head bearings and bottom end bearings inspection and survey
CP/DD2/EN/004 | Thrust bearing to be inspected
CP/DD2/EN/005 | All air bottle survey
CP/DD2/EN/006 | AE Governor Overhaull
CP/DD2/EN/007 | SW Cooling Pump Pipes
CP/DD2/EN/008 | Intermediate Valve overhaul
CP/DD2/EN/009 | Renewal of RO Plant piping
CP/DD2/EN/010 | FW Generator Piping
CP/DD2/EN/011 | LT cooler sea water inlet and outlet pipes to be renewed
CP/DD2/EN/012 | Main Engine air cooler to be cleaned, pressure tested & rapaired as per the below job description .
CP/DD2/EN/013 | Boiler Dump condensor (Atmos condenser) to be cleaned
CP/DD2/EN/014 | All ER coolers to be cleaned
CP/DD2/EN/015 | Centrifugal Pumps Overhaul
CP/DD2/EN/016 | Sea water manifold pipes thickness gauging
CP/DD2/EN/017 | Main Engine crank case - sump tank interconnecting rubber diaphragms to be renewed as necessary.
CP/DD2/EN/018 | Engine Room traveling crane falls to replace & Load Test. S.W.L.4T
CP/DD2/EN/019 | 'Intermediate Shaft bearing
CP/DD2/EN/020 | Bunker Line
CP/DD2/EN/021 | Accomadation AC Evaporator to be changed (02) numbers
CP/DD2/EN/022 | Domestic FW Pipe lines
CP/DD2/EN/023 | Settling Tank Sight Glass
CP/DD2/EN/024 | BWS EUT Pipe
CP/DD2/EN/025 | Boiler sample line
CP/DD2/EN/026 | SW inlet valve to FWG
CP/DD2/EN/027 | ME flow meter FO fixing
CP/DD2/EN/028 | AE flow meter FO fixing
CP/DD2/EN/029 | Sludge and Fuel tank cleaning
CP/DD2/EN/030 | HFO tank Steam Coil Pressure Test

## CP-DD2-EN -001
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -001 |  |  | Chamindra Silva Technical Superintendent |  | NO | Valve | System | DN | Valve Type | Name on plate | Location | Dimentions on Drawing (MPa) | Dimentions from local check (bar)
JOB TITLE: Sea suction and Over Board Valves |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT |  |  |  | Overboard Discharge Valves
Globe Valves , Gate Valves |  |  | Gas free certificate |  | 1 | Ballast Pump 1 to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN350 | Butterfly V. | BMV09 | E/R | 1DN350 | 10DN350
|  |  | Lighting |  | 2 | Ballast Pump 2 to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN350 | Butterfly V. | BMV10 | E/R | 1DN351 | 10DN350
|  |  | Ventilation |  | 3 | Ballast Stipp. Eductor Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN150 | Stop Check v. | BMV16 | E/R | 0.6DN150 | 6DN150
|  | X | Access work |  | 4 | Bilge Eductor for C/H Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN125 | Stop Check v. | BGV27 | E/R | 0.6DN125 | 6DN125
|  | X | Staging |  | 5 | Main Bilge Pump to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN250 | Stop Check v. | BGV13 | E/R | 0.6DN250 | 6DN250
LOCATION: |  |  | Open manhole(s) |  | 6 | Oily Bilge Water Sepatrator to OVBD | E/R Oily Water Separating System | DN40 | Stop Check v. | OWV04 | E/R | 0.6DN50 | 25DN50
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s) |  | 7 | Sewage Discharge OVBD | Sewage Treatment Plant system | DN150 | Storm Vv | SWV01 | E/R | 0.6DN150 | 6DN150
|  |  | Cleaning before |  | 8 | Ref. chamber Discharge OVBD | Layout of Sanitary Drain Piping (Grey water) | DN100 | Stop Check v. | GPV01 | E/R | 2.5DN100 | 25DN100
Engine Room and other Hull valves to be opened, cleaned, overhauled and re-closed with new packing and gaskets and nuts / bolts of yard supply. Yard to furnish labor, materials, tools and tackles, cranes and all necessary works to carry out the following jobs. All sea suction and over board valves to be serviced. Quote as follows, 1. Globe valve to service in place. 2. Globe valve to remove service and pressure test 3. Gate valve to remove service and pressure test |  | X | Cleaning after |  | 9 | Sea Water Cooling Pump to OVBD | Cooling Sea Water System | DN300 | Stop Check v. | CSV19 | E/R | 0.5DN300 | 18DN300
|  |  | Crane |  | 10 | Fresh water Generator Sea Water outlet OVBD | Cooling Sea Water System | DN80 | Stop Check v. | CSV20 | E/R | 0.5DN80 | 5DN80
|  | X | Internal transport |  | 11 | Boiler Blow to OVBD | Feed Water System | DN40 | Boiler Side Drain V. | FEV08 | E/R | 2.5DN32 | 10DN40
|  |  | Transport outside yard |  | 13 | BWTS Back Flushing to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN125 | Butterfly V. | BMV34 | E/R | 1DN125 | 10DN125
|  | X | Paintwork |  | 14 | F.P. TK. Ballast water Overflow to OVBD (P) | Ship's Air, Sounding and Filling Pipes | DN300 | Stop Check v. | AVV101 | Fwd below Boatswain store | 0.6DN300 | 18DN300
|  | X | Pressure Testing |  | 15 | F.P.TK. Ballast Water Overflow to OVBD (S) | Ship's Air, Sounding and Filling Pipes | DN300 | Stop Check v. | AVV102 | Fwd below Boatswain store | 0.6DN300 | 6DN300
|  | X | Function Testing |  | 16 | AFT. Mooring winch Cooling Water to OVBD | Hydraulic diagram of Mooring Winch | DN50 | Stop Check v. | FFV244 | S.G Room |  | 25DN50
|  |  | Fire watch |  | 17 | Bilge Eductor for C/L Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN80 | Stop Check v. | BGV130 | Fwd below Boatswain store | 0.6DN80 | 3DN80
|  |  | Insulation off/on |  |  | Sea Suction Valves
|  | THE WORK TO BE SURVEYED |  |  | 18 | Low Sea Suction | Bilge, Ballast & Fire Fighting System In E/R | DN500 | Remote Controled Butterfly Valve Flanged | CSV24 | E/R | 1DN500 | 10DN500
|  | X | Class Representative |  | 19 | Low Sea Chest Air Vent | Bilge, Ballast & Fire Fighting System In E/R | DN50 | Stop Valve(Bronze) | CSV22 | E/R | 2.5DN50 | 25DN50
|  |  | Maritime Autorities |  | 20 | Low Sea Chest Steam blow | E/R Steam System |  | Stop Valve | STV24 | E/R | 2.5DN15 | 25DN20
|  |  | Manufacturer |  | 21 | From Central FW Cooler | Bilge, Ballast & Fire Fighting System In E/R | DN200 | Stop Check Valve | CSV21 | E/R | 0.6DN200 | 6DN200
|  | X | Owners representative |  | 22 | High Sea Suction | Bilge, Ballast & Fire Fighting System In E/R | DN500 | Remote Controled Butterfly Valve Flanged | CSV25 | E/R | 1DN500 | 10DN500
|  | ATTACHEMNTS |  |  | 23 | High Sea Chest Air Vent | Bilge, Ballast & Fire Fighting System In E/R | DN50 | Stop Valve(Bronze) | CSV23 | E/R | 2.5DN50 | 25DN50
|  |  | Photo |  | 24 | High Sea Chest Steam blow | E/R Steam System |  | Stop Valve | STV25 | E/R | 2.5DN15 | 25DN20
|  |  | Drawing |  | 25 | Emergency F.P Suction Valve | Emergency Fire Pump Room | DN125 |  | EFV01 | E.F.P Room | 0.4DN125 | 4DN125
|  | X | Sketch |  | 26 | E.F.P Sea suction Air pipe | Emergency Fire Pump Room | DN65 | Stop Valve | EFV03 | E.F.P Room | 2.5DN65 | 25DN65
|  |  | Sample |  | 27 | Compressed air blow for sea chest | Emergency Fire Pump Room | DN20 | Stop Valve | EFV04 | E.F.P Room | 2.5DN20 | 25DN20
MATERIAL SUPPLIED BY
|  | X | Yard |  | 28 | Aft Draft Sensor Inlet | Aft Draft Sensor Inlet | DN40 | Globe valve |  | E/R | DN40 | 25DN40
|  |  | Owner |  | 29 | Mid Draft (P) Sensor inlet | Mid Draft (P) Sensor inlet | DN65 | Stop Valve |  | pipe tunnel | DN65 | 16DN25
REMARKS: |  |  |  |  | 30 | Mid Draft (S) Sensor inlet | Mid Draft (S) Sensor inlet | DN65 | Stop Valve |  | pipe tunnel | DN65 | 16DN25
[5 empty] | 31 | FWD Draft Sensor inlet | FWD Draft Sensor inlet | DN25 | Globe valve |  | E.F.P Room | DN25 | 25DN25

## CP-DD2-EN -002
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -002 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Boiler Repairs |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Boiler Repairs - SAACKE MARINE SYSTEMS Suedweststrasse 13, 28237 Bremen, GERMANY Composite Marine Boiler - CMB-VS-1.5+0.9/6 Customer: Weihai SY / Classification: Det Norske Veritas (DNV) Burner type: SKVJ-M 14 / Serial 03812699 Technical Documentation - SAACKE / BA-SKVJM-02ga |  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  | X | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Quote as follows, 1. Two nos of safety valves to be removed and taken to the work shop. Both valves to be overhauled and to be presented to surveyor. After fitting back in place both safety valves are to be tested at set pressure with boiler firing (7.7bar). 2. One safety valve mounting flange seat on the boiler found leaky due to erosive damage on the flange seat (boiler side). Once the valve is removed, the flange seat on the boiler side must be inspected and repaired as appropriate. 3. Pressure gauge to be removed and taken to yard for calibration and certificate to be issued. 4. Both smoke side and fire side wet cleaning (HP water on tube wall / with sufficient flow through tubes) to be carried out. 5. Water side to be cleaned 6. Damaged Refractory to be repaired. Allow for 100 kg, yard supplied refractory. 7. Hydro test to be carried out. 8. All Aux. boiler mountings (As per specification here) to be overhauled. Remove full valves from place, overhaul in workshop using yard supplied packings and jointing. Refit back in good order. (jobs to be done attending surveyors’ satisfaction) 9. Auxiliary Boiler fuel oil flow meter to be calibrated. 10. Auxiliary boiler burner assembly and associated fuel system to be overhauled. 11. Automation function and burner automatic operation must be confirmed. |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
|  | X | Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -003
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -003 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Main Engine Repairs |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Type: MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 |  |  | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
Cleaning before
Main engine all units (05) Complete overhaul, main bearings, cross head bearings and bottom end bearings inspection and survey Quote As follows 1. Inspection of Main Bearing and record of clearance 2. Inspection of Cross Head bearing and record of clearance 3. Inspection Of crank Pin Bearing and Record of clearance 4. Cylinder head overhaul 5. Complete Unit overhaul |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -004
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -004 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Thrust Bearings |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 |  |  | Gas free certificate
|  | X | Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
Cleaning before
Thrust bearing covers to be open up and to be presented to class Surveyor and clearances to be taken and recorded. |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -005
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -005 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Main Air Bottle Survey |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
2 Starting air bottles - Type: A5.0-3.0 Vol: 5m3, Press: 3MPa Control air - Type:A0.25-0.7 Vol:0.25m3, Press: 0.7MPa Emergency air - Type: A0.25-3.0 Vol: 0.25m3, Press: 3MPa Service air - Type: A1.5-0.7 Vol: 1.5m3, Press: 0.7MPa |  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
Cleaning before
1. Air bottles to be open up, clean and presented to surveyor. And top be boxed back using yard supply jointing’s ( Lump Sum Price to quote). 2. Relief valve to be removed from air bottles, overhaul and pressure tested and fixed back. |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -006
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -006 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: AE Governor Overhaull |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Model : ZEXEL Governor model RHD6 Serial No: Gen 1 - 30204003, Gen 2 - 45629006, Gen 3 - 45629004 |  |  | Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
Cleaning before
Aux. Engine govrrnors (03 Nos) to be removed from engines, to be overhaull /serviced in work shop and to be fixed back. Function test to be carried out after fixing to engines. Quote per Piece. |  | X | Cleaning after
|  | X | Crane
|  | X | Internal transport
Transport outside yard
Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -007
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -007 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: SW Pipes |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Sea Water cooling pumps (03 Nos) discharge pipes (between the pump and discharge valve) to be replaced. (Follow the sketch and line diagram) Quote per Piece including removing , refitting and coating with yard supplied materials. |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -008
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -008 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: ER Intermediate Valves |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Below mentioned valves to be dismounted, serviced, pressure tested and fixed back Quote as follows 1. DN 250 Butterfly valves - 06 pcs (SW Cooling pp suction & discharge) / (CSV01, CSV02, CSV03, CSV04, CSV05, CSV06) 2. DN 250 Butterfly check valves - 03 pcs (SW Cooling pp discharge) / (CSV28, CSV29, CSV30) 3. DN 500 Butterfly valves - 02 pcs (High & Low sea chest strainer inboard V/V)/ (CSV26, CSV27) 4. DN 250 Butterfly valves - 05 pcs (Central coolers inlet & outlet) / (CSV17, CSV07, CSV08, CSV12, CSV11) 5. DN 250 Butterfly valves - 04 pcs (Central coolers back flushing) / (CSV13, CSV14, CSV09, CSV10) 6. DN 200 Butterfly valves - 02 pcs (Bilge & GS pp suction + Fire & GS pump suction) / (FFV01, FFV02) 7. DN 350 Hyd. Butterfly valve - 02 pcs (Ballast pump suction valves) / (BWV01, BWV02) 8. DN 350 Hyd. Butterfly check valve - 02 pcs (Ballast pump suction valves) / (BWV42, BWV43) 9. DN 80 Butterfly valve - 01 pc (Ejector pump suction) / (CSV 15) 10. DN 25 Butterfly valve – 01 pc (RO Plant Suction) |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -009
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -009 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: SW Piping |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Renewal of RO Plant piping as per attached drawings. Old pipings to be removed and yard fabricated, coated pipes to be installed using yard supply materials. Outer diameter- 35 mm Seamless shedule 80 Aprx: Length - 35mtrs Quote Lump sum per Piece ll inclusive’ 1. RO sand Filter to Micro Filter Line 2. RO Plant Neutralize filter inlet line 3. To Ro Micro filter line 4. RO Sand filter outlet 5. Brine Reject Line 1 6. Brine Reject line 2 7. RO Plant Outlet connection |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -010
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -010 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: SW Piping |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
FW generator piping. Old pipings to be removed and fabricated and coated pipes to be installed using yard supply materials. Nominal diameter- 90 mm Seamless - shedule 80 drawings are attached. Quote Lump Sum Price; 1. FWG Ejectore to Overboard 2. FWG Feed Pump Filter |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -011
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -011 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: SW Pipes |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
1. LT coolers Sea Water inlet pipe reducers (02 Nos) fabricate and replace (quote All inclusive including coating) 2. LT Cooler SW outlet & Backwash Pipe Manifold to be fabricated and to be fitted (Quote all inclusive including coating) |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -012
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -12 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Main Engine Air Cooler |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 |  |  | Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Quote following jobs main Engine Air cooler 1. Ultrasonic Cleaning: Air cooler to be removed from place, transported to w/shop for cleaning & pressure test and to be refitted after completion of all jobs. 2. Chemical Cleaning Air cooler to be removed from place, transported to w/shop for cleaning & pressure test and to be refitted after completion of all jobs. 3. Sacrificial Zn anodes to be replaced (material yard supply) 4. Cooler to be pressure tested to 5 bar in presence of owner 5. Plug leaky tube 6. Renew, leaky or clogged tube 7. Clear Clogged tube |  | X | Cleaning after
|  | X | Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
Following accessory work would be necessary: a. Engine room bolted cover on funnel deck to be removed. b. Removal of sw piping with valves to and from air cooler front to be removed with railings in way to be removed. c. All fittings to be reinstated to their original state after completion. d. Epoxy coating to be applied on internal surfaces of both covers.

## CP-DD2-EN -013
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -13 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Boiler Dum Condensor |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Maker : Taixing Navigation Machinery Factory Product No : 151594 Type : TRJ2.0/20 |  |  | Gas free certificate
Lighting
Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Qoute for : Main Boiler steam condenser to remove from the position and to be chemically cleaned and to be pressure tested to 10 bar, Refitted with new gaskets and to be tested on board for leaks. |  | X | Cleaning after
|  | X | Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -014
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -014 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Heat Exchangers |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Maker: TRANTER Heat Exchangers (Beijing) Co. Ltd |  |  | Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Quote As follows 1. Central Plate type cooler 2. Lt plate cooler 3. Main lube oil plate cooler 4. ME Jacket water plate type cooler 5. AE lube oil tubular cooler |  | XX | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -015
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS |  |  |  | LO Pump
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -0015 |  |  | Chamindra Silva Technical Superintendent |  | Type : | Deep well type Centrifugal Pump
JOB TITLE: Centrifugal Pumps |  | TO BE INCLUDED |  |  | Discharge Pressure : |  | 0.45 MPa
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT |  |  | Suction Pressure : |  | 0 Mpa
|  |  | Gas free certificate |  | Capacity : | 270 m3/h
|  | X | Lighting
Ventilation
|  | X | Access work |  | ME Jacket Water pump
Staging
LOCATION: |  |  | Open manhole(s) |  | Type : | Centrifugal Pump
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s) |  | Discharge Pressure : |  | 0.30 Mpa
|  | X | Cleaning before |  | Suction Pressure : |  | 0 Mpa
Quote As follows 1. Lube oil pump 02 nos 2. ME Jacket water pump 02 nos 3. LT Cooling Pump 02 nos 4. Cooling Sea water pump 02 nos |  | X | Cleaning after |  | Capacity : | 100 m3/h
Crane
Internal transport
|  |  | Transport outside yard |  | LT Cooling FW Pump
|  | X | Paintwork
|  | X | Pressure Testing |  | Type : | Centrifugal Pump
|  | X | Function Testing |  | Discharge Pressure : |  | 0.35 Mpa
|  |  | Fire watch |  | Suction head : |  | 0 Mpa
|  |  | Insulation off/on |  | Capacity : | 290 m3/h
THE WORK TO BE SURVEYED
|  | X | Class Representative
|  |  | Maritime Autorities |  | Cooling S.W. Pump
Manufacturer
|  | X | Owners representative |  | Type : | Centrifugal Pump
|  | ATTACHEMNTS |  |  | Discharge Pressure : |  | 0.25 Mpa
|  |  | Photo |  | Suction head : |  | 0 Mpa
|  |  | Drawing |  | Capacity : | 320 m3/h
|  |  | Sketch |  | Capacity : | 290 m3/h
Sample
MATERIAL SUPPLIED BY
|  | X | Yard |  | Cooling S.W. Pump
Owner
REMARKS: |  |  |  |  | Type : | Centrifugal Pump
[5 empty] | Discharge Pressure : |  | 0.25 Mpa
[5 empty] | Suction head : |  | 0 Mpa
[5 empty] | Capacity : | 320 m3/h

## CP-DD2-EN -016
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -16 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: UT Gauging |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
Cleaning before
UT gauging to be carried out in Engine room pipings and other required loactions as advised by the owner . Quote per point. |  |  | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
Pressure Testing
Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
IF minimum points applicable to be notified.

## CP-DD2-EN -017
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -17 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Main Engine Sump |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 |  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Main Engine crank case - sump tank interconnecting rubber diaphragms to be renewed after Inspection. Quote per Piece. |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -018
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -018 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Engine room Crane |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
Lighting
Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
Cleaning before
1. Engine room crane falles to be changed. 2. Load Test (05 T) to be carried out on presence of DNV Surveyor. |  |  | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -019
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -019 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Shaft Bearing |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
To be quote as below, a) Intermediate shaft bearing to be opened up and to be presented to class surveyor for inspection. And to be closed back b) Polish the Shaft and Bearings (Top & Bottom halves). b) Load test of the bearing to be carried out and the report to be submitted. |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -020
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -020 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Bunker Line |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
Lighting
Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Complete Bunker line to be pressure tested to 7 bar |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
|  | X | Pressure Testing
Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -021
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -021 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: ACC Ac evaporator |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Acommadation AC evaporator Coils to be renewed with owner supply spares. (02 Nos). Quote per piece all inclusive. |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
Job to be carried ou overnight untill completeion since Crew living without Air Conditioning.

## CP-DD2-EN -022
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -022 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Doestic FW line |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Domestic Fresh Water Supply piping system pipes s to be renewed as per the drawings and diagrams attached Pipes to be fabricated, coated as appropriate and mounted. Approximate dimensions listed in the attached drawings. Quote; 1. Accommodation FW Outlet 2. Accommodation FW line |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | CX | Owners representative
ATTACHEMNTS
Photo
Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -023
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -023 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Settling tank Sight Glass |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
Cleaning before
No.01 & No.02 H.F.O. Settling tank sight glasses (02 Nos) replacing with new. The sight glass material seems to be degraded and therefore translucent. Quote to renew sight Glass with Yard supply Material (02 Nos) |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
|  | X | Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
|  | X | Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
Matrerial should be High tempered unbreakble Glass which does not exist HFO stains

## CP-DD2-EN -024
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -024 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: BWS SW Pipes |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Ballast Water Treatment Syetem EUT unit inlet pipe should be replaced. Quote; Pipe to be fabricated, coated as appropriate and mounted. Approximate dimensions listed in the attached drawings. |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | CX | Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -025
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -025 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Sample Point- Boiler |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Guidance on Fitting of new fuel oil sampling point to Aux. Boiler. • Different fuel oil grades to be used shall be taken into account and the sampling point location to be downstream of the in use fuel oil service tank and as close to the consumer as safely feasible, considering FO temperature, pressure and flow-rate. • The sampling points shall be provided with a shut-off valve and (preferably also with a self-closing valve). • Sampling valve shall be provided with caps to prevent leakage when not in use. • Sampling valve shall be easily accessible in a well-lit and ventilated location. • Sampling valve shall be so located that any drip or spray cannot reach a hot surface, electrical equipment or other source of ignition. • Sampling valve shall be made of ductile material, such as nodular cast iron or steel • Pressure ratings of flanges/valve - shall not be lower than the maximum working pressure of the FO system (6 bar) • Drip trays shall be arranged below the sampling points to ensure suitable drainage to a drain tank. • The installation shall be subjected to a function test before showing it to Class • The sampling point to be designated and clearly marked both in the ER and on the relevant piping diagram. Quote Lump Sum For the Job |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
Paintwork
Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
Job to be completed as satisfaction to class rules and attending surveyors satisfaction.
AA

## CP-DD2-EN -026
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -026 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: New valve to FWG |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
New butterfly valve (owner supplied) to be installed to the Freshwater generator ejector pump suction piping. Valve to be installed using yard supply materials and accessoriness’s close as possible to the sea chest. Quote Lump sum price for the completion of the Including NDT. (DYE test and Ultra sound test- Report to submit) 2. |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
|  | X | Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -027
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -027 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: ME Flow Meters |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  | X | Dismantle floorplate(s)
|  | X | Cleaning before
Flow meters to be fixed(02 nos) to ME supply and return line as per attached drawing. Flow meters will be supplied by owner and other all required material to be supplied by yard. Required lagging to be applied , flanges to be covered by antisplash tapes. Catch Tray to be fabricated under the flow meter and drain line to be connected below drain line. Line to be pressure tested after fabrication works. Before start work fuel lines to be completely drained. Lum sum price to be quoted for the complete Job |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
|  | X | Fire watch
|  | X | Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
|  | X | Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -028
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -028 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: AE Flow meters |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
|  | X | Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Flow meters to be fixed(02 nos) to AE supply and return line as per attached drawing. Flow meters will be supplied by owner and other all required material to be supplied by yard. Required lagging to be applied , flanges to be covered by antisplash tapes. Catch tary to be fabricated and drain line to be connected to drain line below. Line to be pressure tested after fabrication works. Before start work fuel lines to be completely drained. Lum sum price to be quoted for the complete Job |  | X | Cleaning after
Crane
|  | X | Internal transport
Transport outside yard
|  | X | Paintwork
|  | X | Pressure Testing
|  | X | Function Testing
|  | X | Fire watch
|  | X | Insulation off/on
THE WORK TO BE SURVEYED
Class Representative
Maritime Autorities
Manufacturer
Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:
All dimensions indicated in the drawing are for quotation purposes only. The contractor shall verify and carry out fabrication in accordance with the existing pipeline configuration on board.

## CP-DD2-EN -029
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -029 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Fuel & SludgeTank Cleaning |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
Access work
Staging
LOCATION: |  |  | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
Manhole to be opened. Tank to be provided with ventilation fan and lighting. Gas free certificate required for man entry to be included. Carry out cleaning of the tank and allow to remove and dispose off the remaining sludge. All sludge removed to be disposed off as per the local regulation and certificate issued for the quantity of sludge removed. Tank manhole to be closed with new gasket supplied by yard. Quote for below Tanks; 1. HFO Purifier Sludge Tank – 8.2 m3 2. Sludge Tank – 41.68 m3 3. HFO Set Tank – 20 m3 (02 Nos) 4. HFO Ser Tank – 20 m3 (02 Nos) 5. HFO Staorage DB Tank -460 m3 (03Nos) 6. HFO Over Flow tank -70 m3 7. Bilge water tank -42m3 8. Remove Sludge per Cum (Aprox: 12 m3) |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
Pressure Testing
Function Testing
Fire watch
Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS:

## CP-DD2-EN -030
MV "CEYLON PRINCESS" | SPECIFICATION OF REPAIRS
JOB NUMBER | DATE |  | Authorized by | Signature
CP-DD2-EN -030 |  |  | Chamindra Silva Technical Superintendent
JOB TITLE: Tank Heating Coil |  | TO BE INCLUDED
MAKERS DETAILS, SERIAL NO, MACHINERY / EQUIPMEN DETAILS. |  | SPECIAL REQUIREMENT
|  | X | Gas free certificate
|  | X | Lighting
|  | X | Ventilation
|  | X | Access work
Staging
LOCATION: |  | X | Open manhole(s)
DETAILED SPECIFICATION INCL.SIZE,AMOUNT,DIMENSION,MATERIAL,ETC. |  |  | Dismantle floorplate(s)
|  | X | Cleaning before
HFO Tank steam heating coils to be pressure tested to 10 Bar. (tan k List Is attached) |  | X | Cleaning after
Crane
Internal transport
Transport outside yard
Paintwork
|  | X | Pressure Testing
Function Testing
Fire watch
|  | X | Insulation off/on
THE WORK TO BE SURVEYED
|  | X | Class Representative
Maritime Autorities
Manufacturer
|  | X | Owners representative
ATTACHEMNTS
Photo
Drawing
Sketch
Sample
MATERIAL SUPPLIED BY
|  | X | Yard
Owner
REMARKS: