## DD1 DK 024
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | M/V CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/024 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
[6 empty] | x | Class Representative
Pipe Lines on Main Deck | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
1. Fire line on main deck port side to be turned upside down & re clamped. Expansion joints to be inspected and gasket renewed | [6 empty] | Gas free certificate
Lighting
2.Cracks on.Junction boxes near No.3C.H to be inspected and fabricated | [6 empty] | Ventilation
3.Old U clamps of hydraulic lines, fresh water lines, compressed air lines on main deck to be removed. Clamping area to be thoroughly cleaned of rust, re-painted and new clamping to be carried out. Lead sheet to be put below clamps. | [6 empty] | Cleaning before
[6 empty] | x | Cleaning after
[6 empty] | x | Staging
Crane service
4. mild steel nuts & bolts to be replaced with SS | [6 empty] | Transportation internal
5.'Fire line pressure test | [6 empty] | Transportation outside yard
Note: Above items’ job scope to be verified at site | [5 empty] | x | Access work
Corrosion protection
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Galvanizing
[6 empty] | x | Paintwork (T/Up, Full Coat)
Pressure testing
AS per the attachment | [6 empty] | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements | [5 empty] | Sub contract
Main Deck - Port side | [5 empty] | Other details
Materials
[6 empty] | x | Yard supply
[6 empty] | x | Owner’s supply
Maker’s supply
Enclosures
[6 empty] | x | Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 025
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | M/V CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/025 | JOB No. |  | JOB No.
Date : | 02.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
Cleaning and painting of chain lockers | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Gratings to be removed, cleaned and put back upon completion of related work.All mud / scale to be removed from chain lockers.Entire Lockers to be cleaned/scraped and coated with owner supplied paint to the satisfaction of the chief officer to a height of 3 m from the bottom of the locker. | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Staging
Crane service
Type of paint : -Bitumen solition 1*150 microns | [6 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements | [5 empty] | Sub contract
F'CLE DECK
Other details
Materials
Yard supply
[6 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 026
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | M/V CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/026 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
Transducer of Echo sounder/Doppler logs check and clean. | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Transducer of Echo sounder/Doppler logs check and clean. | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Staging
Crane service
Transportation internal
As per the attachment | [6 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements | [5 empty] | Sub contract
Void space below the emergency fire pump room
Other details
Materials
Yard supply
[6 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 027
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/027 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
Maintenance of Grabs | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Maker - Shanghai Guanbo Machinery & Equipment Co.Ltd | [6 empty] | Underwriters
Grab type - RC 0246 - 6 - 12 | [6 empty] | Others
Actual Job description | [5 empty] | Yard work to be included
All five grabs to be inspected and replaced all wasted and deformed steel structures ( Supporting H beams , Box structure ) | [6 empty] | Gas free certificate
Lighting
Ventilation
All grabs to be blasted and painted | [6 empty] | Cleaning before
[6 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | x | Staging
Crane service
[6 empty] | x | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
[6 empty] | x | Paintwork (T/Up, Full Coat)
Pressure testing
[6 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements | [5 empty] | Sub contract
Main deck- cross deck no.1, no.2 , no.4 and no.5 | [5 empty] | Other details
Materials
[6 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
[6 empty] | x | Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  |  | Sketch
[6 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 028
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | M/V CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/028 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
[6 empty] | x | Class Representative
BRAKE RENDERING TEST FOR MOORING WINCH | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Actual Job Description: - Brake rendering tests to be carried out for the following winches:- 1) Mooring winch Fwd , Port & Stbd 2) Mooring winch Aft, Port & Stbd Tests to be witness by Class surveyor and attending vessel superintendent. Brake rendering test report and certificate to be provided to owner’s representatives / Owner’s superintendent. | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Pressure testing
[6 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirement | [5 empty] | Sub contract
Both STBD & PORT sides drums in FWD and AFT. | [5 empty] | Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
[6 empty] | x | Drawing
Prepared by |  |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 029
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/029 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
Maintenance of upper deck common W.C | [6 empty] | Flag Sate Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Renewal of damage drain lines of wash basin | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[6 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[6 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements | [5 empty] | Sub contract
Upper deck - Port side | [5 empty] | Other details
Materials
[6 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  |  | Approved by Manager SMT |  |  | Sketch
[6 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 030
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | M/V CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/030 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
De-mucking of ballast tanks - FPK , APK , WBT-NO.1P&S , 2P&S , 3P&S , 4P&S, 5P&S | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Ballast tanks lower sections (up to height of inner bottom) and bottom shell plating with internals to be HP washed and water pumped out. | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[6 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
[6 empty] | x | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements | [5 empty] | Sub contract
FPK Tank | [5 empty] | Other details
APK Tank
NO.1 P&S
NO.2 P&S
NO.3 P&S | [5 empty] | Materials
NO.4 P&S | [5 empty] | x | Yard supply
NO.5 P&S | [6 empty] | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 031
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | CEYLON PRINCES
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/031 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
Extend Grab securing arms or change the securing points | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Extend Grab securing arms anaother one meter 45 degrees towards vertical or change into convenient place, where the crane head able to reach. | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[6 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Staging
Crane service
'Steel plates Thickness - 20mm¦ | [6 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirement | [5 empty] | Sub contract
CrossBay decks
Other details
Materials
[6 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  |  | Sketch
[6 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 032
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/031 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
Buildup of Anchor cable stopper (P&S) and painting. | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Worn out running of the cable stopper to be built up by welding using hard facing electrode. Required welding procedure must be submitted prior to commencement of job. | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[6 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
[6 empty] | x | Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirement | [5 empty] | Sub contract
FORECASTLE DECK | [5 empty] | Other details
Materials
[6 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  |  | Sketch
[6 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## DD1 DK 033
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | CEYLON PRINCESS
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CP/DD1/DK/033 | JOB No. |  | JOB No.
Date : | 03.04.2021 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
[6 empty] | x | Class Representative
Overhaul of Fairlead Rollers | [6 empty] | Flag State Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Thorough cleaning to be carried out. To be inspected along with ship’s staff for wear and tear / defects / damage. Parts that require repairs to be re-conditioned or replaced. Ensure grease / lubrication channels are clear. Adequate lubrication / grease to be applied and rollers installed back in position. Each roller to be checked for free movement after refitting | [5 empty] | x | Gas free certificate
Lighting
Ventilation
[6 empty] | x | Cleaning before
[6 empty] | x | Cleaning after
Staging
Crane service
Transportation internal
Transportation outside yard
[6 empty] | x | Access work
Corrosion protection
Galvanizing
[6 empty] | x | Paintwork (T/Up, Full Coat)
Pressure testing
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Function testing
Non-destructive test
[6 empty] | x | Correction drawings
Location, material, access work, staging, other details & special requirement | [5 empty] | Sub contract
FWD AND AFT MOORING STATIONS | [5 empty] | Other details
Materials
[6 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
[6 empty] | x | Drawing
Prepared by ; |  |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date