## Index
SPECIFICATION OF REPAIRS (DOCKING) - (INDEX- Engine)
M.V. | Ceylon Breeze |  |  | Date: | 2025-09-06
Job No | Description | Delegation | Requisition No | Reqn Status | Remarks
EN/001 | All sea suction and overboard valves.
EN/002 | Stern tube seals and chrome liner inspection.
EN/003 | Propeller inspection
EN/004 | Rudder and rudder carrier bearing inspection
EN/005 | Boiler internal and external inspection and survey
EN/006 | Main engine all units main bearings, cross head bearings and bottom end bearings inspection and survey
EN/007 | Thrust bearing to be inspected
EN/008 | All air bottle survey
EN/009 | Main engine turbocharger overhaul.
EN/010 | All auxiliary engine governor overhaul
EN/011 | All three main S.W Pump discharge pipe line elbow renewal.
EN/012 | All main S.W Pump discharge butterfly valves to replaced with NR valves
EN/013 | Main Engine all five unit fuel oil pressure boosters to be overhauled
EN/014 | Main Engine unit No 1,2,3 and 4 to be overhauled
EN/015 | Renewal of RO Plant piping
EN/016 | Isolation valve to be fitted to FWG Suction line from Main Pipe.
EN/017 | Deck Crane No 3 and No 4- Jib Bearings to be replaced.
EN/018 | BWMS pneumatic operated valve from flow meter to be serviced
EN/019 | LT cooler sea water inlet and outlet pipes to be renewed
EN/020 | Main Engine air cooler to be cleaned, pressure tested & rapaired as per the below job description .
EN/021 | Boiler Dump condensor (Atmos condenser) to be cleaned
EN/022 | All ER coolers to be cleaned
EN/023 | Provision crane rack to be inspected and rapaired as necessary.
EN/024 | Waste oil tank extractor fan and air bubbling arrangement to be fitted
EN/025 | CSM Items : No 1 and No 2 M/E LO Pump, No 1 and No 2 M/E Jacket water pump, No 1, No 2 and No 3 LT cooling pump, No 1 and No 3 Main Sea water pump
EN/026 | Emergency Fire pump discharge valve need to be overhaul or renew as per owner's advice.
EN/027 | All Sea water manifold pipes thickness gauging tobe done & repair?renew as per owners advice.
EN/028 | Mai Engine main startig air automatic valve to be serviced.
EN/029 | Main Engine crank case - sump tank interconnecting rubber diaphragms to be renewed as necessary.
EN/030 | Main Engine accumilators to be serviced as per the makers specification.
EN/031 | Main Engine FIVA & cylinder lubricator units to be serviced as per Maker Specifications.
EN/032 | Main Engine HPS Hydrolic pumps to be serviced & cuppling spider to be renewd as necessary
EN/033 | 'Co2 system all flexible hoses 10 year renewal to be carried out.
EN/034 | Hot water hydrophore tank leacky botom shell plate to be croped & renewed
EN/035 | Primary billge tank bottom plating corroded section (300mm X 300mm), to be cropped & renewed.
EN/036 | HFO bunker manifold both the filters to be rapaired or fabricated as per owners advice.
EN/037 | Shaft bearing to be opene up inspected presented to the survey & boxed up. Clearence to be taken & recorded
EN/038 | Windlass (Stbd) hydrolic mootor slow operation to be investigated & serviced accordingly.
Note: REPAIR SPECIFICATION NUMBERING TO CONTINUE AS FOLLOWS:
DECK / RADIO DEPARTMENT: D-001 ～D-999
ENGINE / ELECTRICAL DEPARTMENT: E-001 ～E-999

## EN001
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/001 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
All sea suction and overboard valves. Valve Specifications details attached in the DD Specification Document and Annex 001 sheet. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All sea suction and overboard valves to be removed, lapped or renewed as per the condition, pressure tested and assembled back. | [5 empty] | Gas free certificate
Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Valve Specifications details attached in annex 001 |  |  |  |  | x | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Valve location details attached in annex 001
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## Annex 001
| Valve | System | DN | Valve Type | Name on plate | Location | Dimentions on Drawing (MPa) | Dimentions from local check (bar)
Overboard Discharge Valves
1 | Ballast Pump 1 to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN350 | Butterfly V. | BMV09 | E/R | 1DN350 | 10DN350
2 | Ballast Pump 2 to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN350 | Butterfly V. | BMV10 | E/R | 1DN351 | 10DN350
3 | Ballast Stipp. Eductor Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN150 | Stop Check v. | BMV16 | E/R | 0.6DN150 | 6DN150
4 | Bilge Eductor for C/H Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN125 | Stop Check v. | BGV27 | E/R | 0.6DN125 | 6DN125
5 | Main Bilge Pump to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN250 | Stop Check v. | BGV13 | E/R | 0.6DN250 | 6DN250
6 | Oily Bilge Water Sepatrator to OVBD | E/R Oily Water Separating System | DN40 | Stop Check v. | OWV04 | E/R | 0.6DN50 | 25DN50
7 | Sewage Discharge OVBD | Sewage Treatment Plant system | DN150 | Storm Vv | SWV01 | E/R | 0.6DN150 | 6DN150
8 | Ref. chamber Discharge OVBD | Layout of Sanitary Drain Piping (Grey water) | DN100 | Stop Check v. | GPV01 | E/R | 2.5DN100 | 25DN100
9 | Sea Water Cooling Pump to OVBD | Cooling Sea Water System | DN300 | Stop Check v. | CSV19 | E/R | 0.5DN300 | 18DN300
10 | Fresh water Generator Sea Water outlet OVBD | Cooling Sea Water System | DN80 | Stop Check v. | CSV20 | E/R | 0.5DN80 | 5DN80
11 | Boiler Blow to OVBD | Feed Water System | DN40 | Boiler Side Drain V. | FEV08 | E/R | 2.5DN32 | 10DN40
13 | BWTS Back Flushing to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN125 | Butterfly V. | BMV34 | E/R | 1DN125 | 10DN125
14 | F.P. TK. Ballast water Overflow to OVBD (P) | Ship's Air, Sounding and Filling Pipes | DN300 | Stop Check v. | AVV101 | Fwd below Boatswain store | 0.6DN300 | 18DN300
15 | F.P.TK. Ballast Water Overflow to OVBD (S) | Ship's Air, Sounding and Filling Pipes | DN300 | Stop Check v. | AVV102 | Fwd below Boatswain store | 0.6DN300 | 6DN300
16 | AFT. Mooring winch Cooling Water to OVBD | Hydraulic diagram of Mooring Winch | DN50 | Stop Check v. | FFV244 | S.G Room |  | 25DN50
17 | Bilge Eductor for C/L Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN80 | Stop Check v. | BGV130 | Fwd below Boatswain store | 0.6DN80 | 3DN80
Sea Suction Valves
18 | Low Sea Suction | Bilge, Ballast & Fire Fighting System In E/R | DN500 | Remote Controled Butterfly Valve Flanged | CSV24 | E/R | 1DN500 | 10DN500
19 | Low Sea Chest Air Vent | Bilge, Ballast & Fire Fighting System In E/R | DN50 | Stop Valve(Bronze) | CSV22 | E/R | 2.5DN50 | 25DN50
20 | Low Sea Chest Steam blow | E/R Steam System |  | Stop Valve | STV24 | E/R | 2.5DN15 | 25DN20
21 | From Central FW Cooler | Bilge, Ballast & Fire Fighting System In E/R | DN200 | Stop Check Valve | CSV21 | E/R | 0.6DN200 | 6DN200
22 | High Sea Suction | Bilge, Ballast & Fire Fighting System In E/R | DN500 | Remote Controled Butterfly Valve Flanged | CSV25 | E/R | 1DN500 | 10DN500
23 | High Sea Chest Air Vent | Bilge, Ballast & Fire Fighting System In E/R | DN50 | Stop Valve(Bronze) | CSV23 | E/R | 2.5DN50 | 25DN50
24 | High Sea Chest Steam blow | E/R Steam System |  | Stop Valve | STV25 | E/R | 2.5DN15 | 25DN20
25 | Emergency F.P Suction Valve | Emergency Fire Pump Room | DN125 |  | EFV01 | E.F.P Room | 0.4DN125 | 4DN125
26 | E.F.P Sea suction Air pipe | Emergency Fire Pump Room | DN65 | Stop Valve | EFV03 | E.F.P Room | 2.5DN65 | 25DN65
27 | Compressed air blow for sea chest | Emergency Fire Pump Room | DN20 | Stop Valve | EFV04 | E.F.P Room | 2.5DN20 | 25DN20
28 | Aft Draft Sensor Inlet | Aft Draft Sensor Inlet | DN40 | Globe valve |  | E/R | DN40 | 25DN40
29 | Mid Draft (P) Sensor inlet | Mid Draft (P) Sensor inlet | DN65 | Stop Valve |  | pipe tunnel | DN65 | 16DN25
30 | Mid Draft (S) Sensor inlet | Mid Draft (S) Sensor inlet | DN65 | Stop Valve |  | pipe tunnel | DN65 | 16DN25
31 | FWD Draft Sensor inlet | FWD Draft Sensor inlet | DN25 | Globe valve |  | E.F.P Room | DN25 | 25DN25

## EN002
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD | AFT SEAL
|  | JOB No. | CB/DD2/EN/002 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Stern tube seals and chrome liner inspection. Type : STERNGUARD OLS4-P / OLS2-P Maker: Wartsila Japan Ltd., Toyama Factory, Japan | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Stern tube seals and chrome liner inspection to be carried out and renew if required. | [5 empty] | Gas free certificate
renewal or repair as per the condition | [5 empty] | Lighting
System oil to be totally drained, entire system to be flushed & the oil to be change from ME system oil to (Biostat 100). | [5 empty] | Ventilation
[5 empty] | x | Cleaning before
Stern tube bearing clearence to be checked with poker gauge . |  |  |  |  | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Type : STERNGUARD OLS4-P / OLS2-P Maker: Wartsila Japan Ltd., Toyama Factory, Japan | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
FWD SEAL

## EN003
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/003 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Propeller inspection Specification details attached | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Propeller inspection, pull-down and push-up as per condition. | [5 empty] | Gas free certificate
Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
During last under water survey it was noted that one of the propeller blade is damaged. Need to be rapair as necesseary | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
[5 empty] | x | Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN004
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/004 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Rudder and rudder carrier bearing inspection Specification details attached | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Rudder and rudder carrier bearing inspection and repair as per the condition | [5 empty] | Gas free certificate
condition | [5 empty] | Lighting
Rudder pintle & jumper bar clearece to be checked & recorded. | [5 empty] | Ventilation
Rudder bottom plug to be removed, checked for any perforation & pressure check to be carried out. |  |  |  |  | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
[5 empty] | x | Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN005
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/005 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Boiler internal and external inspection and survey | [5 empty] | Flag Sate Representative
Maker: SAACKE Composite Marine Boiler CMB-VS |  |  |  |  | x | Owners Representative
Order no : N143836/2CN Serial : B2-1723 | [5 empty] | Manufacturers' Representative
Dry weight=19600kg | [5 empty] | Underwriters
Water volume=12.0 m3 | [5 empty] | Others
Operating pressure = 6.0 bar
Actual Job description |  |  |  |  | Yard work to be included
Boiler open up, internal and external inspection of fire side, water side and combustion chamber, repair as per condition. | [5 empty] | Gas free certificate
Lighting
Boiler Survey | [5 empty] | Ventilation
Boiler all mountings to be overhauled, safety valves to be overhauled & to floted. |  |  |  |  | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
SAACKE Composite Marine Boiler CMB-VS | [5 empty] | Transportation internal
Transportation outside yard
Serial : B2-1723 | [5 empty] | Access work
Order no : N143836/2CN | [5 empty] | Corrosion protection
Dry weight=19600kg | [5 empty] | Galvanizing
Water volume=12.0 m3 | [5 empty] | Paintwork (T/Up, Full Coat)
Operating pressure = 6.0 bar |  |  |  |  | x | Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN006
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/006 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Main engine all units main bearings, cross head bearings and bottom end bearings inspection and survey | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Type: MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Manufacturers' Representative
Serial No : JMT60-0212 | [5 empty] | Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main engine all units main bearings, cross head bearings and bottom end bearings open up for inspection and survey and assemble back | [5 empty] | Gas free certificate
Lighting
All cleareces to be checked & recorded before & after the job. | [5 empty] | Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 007
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/0007 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Thrust bearing to be inspected and clearence to be checked. MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Thrust bearing to be inspected and clearence to checked & recorded. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 008
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/008 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
All air bottle survey | [5 empty] | Flag Sate Representative
2 Starting air bottles - Type: A5.0-3.0 Vol: 5m3, Press: 3MPa |  |  |  |  | x | Owners Representative
Control air - Type:A0.25-0.7 Vol:0.25m3, Press: 0.7MPa | [5 empty] | Manufacturers' Representative
Emergency air - Type: A0.25-3.0 Vol: 0.25m3, Press: 3MPa | [5 empty] | Underwriters
Service air - Type: A1.5-0.7 Vol: 1.5m3, Press: 0.7MPa | [5 empty] | Others
.
Maker: Jiangsu Yongtai Pressure Vessel CO.LTD
Actual Job description |  |  |  |  | Yard work to be included
All air bottles open up for inspection and survey | [5 empty] | Gas free certificate
Relief valves to be pressure tested on completion of overhaul. | [5 empty] | Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
2 Starting air bottles - Type: A5.0-3.0 Vol: 5m3, Press: 3MPa | [5 empty] | Transportation internal
Control air - Type:A0.25-0.7 Vol:0.25m3, Press: 0.7MPa | [5 empty] | Transportation outside yard
Emergency air - Type: A0.25-3.0 Vol: 0.25m3, Press: 3MPa | [5 empty] | Access work
Service air - Type: A1.5-0.7 Vol: 1.5m3, Press: 0.7MPa | [5 empty] | Corrosion protection
. | [5 empty] | Galvanizing
Maker: Jiangsu Yongtai Pressure Vessel CO.LTD | [5 empty] | Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 009
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/009 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Main engine turbocharger overhaul. | [5 empty] | Flag Sate Representative
MAN Diesel & Turbo |  |  |  |  | x | Owners Representative
Type: TCA55-21246 | [5 empty] | Manufacturers' Representative
Year :2014 | [5 empty] | Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main engine turbocharger overhaul to be carried out acording to the makers specifications all clearences mesurments to be checked & recorded. | [5 empty] | Gas free certificate
Lighting
Ventilation
Static & dynamic balancings to be carried out as per makers specifications. |  |  |  |  | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN Diesel & Turbo |  |  |  |  | x | Transportation internal
Type: TCA55-21246 | [5 empty] | Transportation outside yard
Year :2014 | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Parts to be renewed where necessary using owner supplied spares.
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 010
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/010 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All auxiliary engine governor overhaul Model : ZEXEL Governor model RHD6 Serial No: Gen 1 - 30204003, Gen 2 - 45629006, Gen 3 - 45629004 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All three auxiliary engine governors to be overhauled | [5 empty] | Gas free certificate
Governers to be tested on bench & to be tested on engine. | [5 empty] | Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
ZEXEL Governor model RHD6 | [5 empty] | Transportation internal
Serial No: Gen 1 - 30204003, Gen 2 - 45629006, Gen 3 - 45629004 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Parts to be renewed where necessary.
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 011
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD | Sea water pump discharge line elbow
|  | JOB No. | CB/DD2/EN/011 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All three main S.W Pump discharge pipe line elbows Inspection. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All three main S.W Pump discharge elbows between pump and pump discharge butterfly valves to be inspected & renewed on owners advice. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
267 mm
D= 400 mm
400 mm
650 mm
PCD = 355 mm, 12 Holes
PCD = 355 mm, 12 Holes
385 mm
Seamless Steel (Galvanized)
9.5mm thickness

## EN 012
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/012 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All main S.W Pump discharge valves, NR flap valves and suction butterfly valves to be ispected & repaired or renewed as necessary. Non-return flap valve, 10DN250, Flap height- 125mm, Butterfly valve, wafer type with worm gear, 10DN250 IMPA no:- 752218 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All main S.W Pump discharge NR flap valves and suction butterfly valves to be ispected & repaired or renewed as necessary. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Non-return flap valve, 10DN250, Flap height- 125mm Butterfly valve, wafer type with worm gear, 10DN250 IMPA no:- 752218 | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 013
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/013 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine all five unit fuel oil pressure boosters ( Fuel pump) to be overhauled MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine all five unit fuel oil pressure boosters to be overhauled | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 014
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/014 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine unit No 1,2,3 and 4 to be overhauled MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine unit No 1,2,3 and 4 to be overhauled | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 015
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/015 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Renewal of RO Plant piping. IMPA code- - outer diameter- 42.7mm, nominal size- 1-1/4,Seamless shedule 80 Length - 35mtrs | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Renewal of RO Plant low pressure pump suction and discharge piping from sea suction valve to the RO plant | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
IMPA code - Steel pipe; Carbon steel, galvanized, outer diameter- 42.7mm, nominal size- 1-1/4, Shedule 80, Length- 35mtrs | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 016
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/016 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Renewal of Fresh water generator piping. IMPA code- - DN 100,Seamless shedule 80 Length - 35mtrs | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Renewal of Fresh water generator piping. IMPA code- - DN 100,Seamless shedule 80 Length - 35mtrs | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
IMPA code- - DN 100,Seamless shedule 80 Length - 35mtrs | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 017
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/017 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Deck Crane No 3 and No 4- Jib Bearings to be replaced. Macgregor Crane Type: GLB3030-2/2430gr | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Deck Crane No4- Jib Bearings to be replaced. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Macgregor Crane | [5 empty] | Transportation internal
Type: GLB3030-2/2430gr | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 018
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/018 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
BWMS pneumatic operated valve from flow meter to be serviced | [5 empty] | Flag Sate Representative
OceanGuard Ballast Water Management System BWMS Model: HMT-1000 |  |  |  |  | x | Owners Representative
Maker : HEADWAY TECHNOLOGY CO.LTD | [5 empty] | Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
BWMS pneumatic operated valve from flow meter (BWV 31) DN 350, PN 1.0 Mpa, to be service. Fore peak ballest valve actuator to be overhauled. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
OceanGuard Ballast Water Management System BWMS Model: HMT-1000 | [5 empty] | Transportation internal
Transportation outside yard
Maker : HEADWAY TECHNOLOGY CO.LTD | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 019
CEYLON SHIPPING CORPORATION LTD
[7 empty] | Sea Water In (2 pipes for 2 LT Coolers) | Sea Water Out (2 pipes with different lengths for 2 LT coolers)
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/019 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
LT cooler sea water inlet to be renewed | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
LT cooler No1 and No2 sea water inlet and outlet pipes ( total 4 pipes) which are ungalvanized sacrificer pipes of the LT coolers to be renewed with Zn sacrificing anodes fitted | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
D= 285 mm
D= 375 mm
230 mm
PCD = 240mm, 8 Holes
PCD = 335 mm, 12 Holes
285 mm
285 mm
D= 285 mm, 8 holes
Port side Flange to Flange = 190 mm
Stbd side Flange to Flange = 245 mm

## EN 020
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD1/EN/020 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine air cooler to be cleaned, pressure test & rapaired as per the below job description . MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Yard work to be included
Gas free certificate
Cooler leaky tubes to be renewed or plugged as necessary. | [5 empty] | Lighting
OR Cooler segment to be replaced with owener supplied new spare. | [5 empty] | Ventilation
To be pressure tested on completion of the job at presence of owner representative. |  |  |  |  | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 021
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/021 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Boiler Dump condensor (Atmos condenser) to be cleaned Maker : Taixing Navigation Machinery Factory Product No : 151594 Type : TRJ2.0/20 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Boiler Dump condensor (Atmos condenser) to be cleaned & pressure tested. | [5 empty] | Gas free certificate
Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker : Taixing Navigation Machinery Factory | [5 empty] | Transportation internal
Type : TRJ2.0/20 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 022
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD | No 1 Central LT Cooler
|  | JOB No. | CB/DD2/EN 022 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All engine room coolers to be cleaned Maker: TRANTER Heat Exchangers (Beijing) Co. Ltd | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All engine room coolers to be cleaned including both LT coolers, Main Engine jacket and LO cooler, aux engine jacket and LO coolers. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker: TRANTER Heat Exchangers (Beijing) Co. Ltd | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
No 2 LT Cooler
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
Main L.O Cooler
Jacket Water Cooler
AE Lube Oil Cooler

## EN 023
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/023 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Provision crane's rack to be inspected & rpaired as necessary. Maker : Jiangyin Concrane Equipment CO.LTD Type : C4PC Serial : C4PC 15WA SWL: 4 T | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Provision crane's rack to be inspected & rpaired as necessary. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker : Jiangyin Concrane Equipment CO.LTD Type : C4PC | [5 empty] | Transportation internal
Transportation outside yard
Serial : C4PC 15WA | [5 empty] | Access work
SWL: 4 T | [5 empty] | Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 024
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/024 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Waste oil tank extractor fan and air bubbling arrangement to be fitted | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Extractor fan and air bubbling arrangement to be fitted on top of waste oil tank and connected to the exsisting vent line which leads to the mist box | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 025
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/025 | JOB No. |  | JOB No.
Date : |  | Account Number |  |  |  |  | LO Pump
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[6 empty] | Class Representative | Type : | Deep well type Centrifugal Pump
CSM Items : No 1 and No 2 M/E LO Pump, No 1 and No 2 M/E Jacket water pump, No 1, No 2 and No 3 LT cooling pump, No 1 and No 3 Main Sea water pumps, to be overhauled with owner supplied spares. | [5 empty] | Flag Sate Representative | Discharge Pressure : |  | 0.45 MPa
[5 empty] | x | Owners Representative | Suction Pressure : |  | 0 Mpa
[6 empty] | Manufacturers' Representative | Capacity : | 270 m3/h
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included |  | ME Jacket Water pump
CSM Items : No 1 and No 2 M/E LO Pump, No 1 and No 2 M/E Jacket water pump, No 1, No 2 and No 3 LT cooling pump, No 1 and No 3 Main Sea water pump | [5 empty] | Gas free certificate
[6 empty] | Lighting | Type : | Centrifugal Pump
[6 empty] | Ventilation | Discharge Pressure : |  | 0.30 Mpa
[6 empty] | Cleaning before | Suction Pressure : |  | 0 Mpa
[6 empty] | Cleaning after | Capacity : | 100 m3/h
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
[6 empty] | Transportation internal | LT Cooling FW Pump
Transportation outside yard
[6 empty] | Access work | Type : | Centrifugal Pump
[6 empty] | Corrosion protection | Discharge Pressure : |  | 0.35 Mpa
[6 empty] | Galvanizing | Suction head : |  | 0 Mpa
[6 empty] | Paintwork (T/Up, Full Coat) | Capacity : | 290 m3/h
Pressure testing
[5 empty] | x | Function testing
[6 empty] | Non-destructive test | Cooling S.W. Pump
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract |  | Type : | Centrifugal Pump
[7 empty] | Discharge Pressure : |  | 0.25 Mpa
[7 empty] | Suction head : |  | 0 Mpa
[5 empty] | Other details |  | Capacity : | 320 m3/h
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 026
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/026 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Emergency Fire pump discharge valve need to be overhaul or renew as per owner's advice. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Emergency Fire pump discharge valve need to be overhaul or renew as per owner's advice. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 027
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/027 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All Sea water manifold pipes thickness gauging tobe done & repair?renew as per owners advice. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All Sea water manifold pipes thickness gauging tobe done & repair?renew as per owners advice. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 028
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/028 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Mai Engine main startig air automatic valve to be serviced. MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Mai Engine main startig air automatic valve to be serviced. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 029
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/029 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine crank case - sump tank interconnecting rubber diaphragms to be renewed as necessary. MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine crank case - sump tank interconnecting rubber diaphragms to be renewed as necessary. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 030
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/030 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine accumilators to be serviced as per the makers specification. MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine accumilators to be serviced as per the makers specification. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 031
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/031 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine FIVA & cylinder lubricator units to be serviced as per Maker Specifications. MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine FIVA & cylinder lubricator units to be serviced as per Maker Specifications. . | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 032
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/032 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine HPS Hydrolic pumps to be serviced & cuppling spider to be renewd as necessary. Engine driven pump - 3 Nos & Electrical driven 2 Nos. MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine HPS Hydrolic pumps to be serviced & cuppling spider to be renewd as necessary. Engine driven pump - 3 Nos & Electrical driven 2 Nos. HPS system hoses, seals & O-rings to be renewed as per makers specifications. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 033
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/033 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Co2 system all flexible hoses 10 year renewal to be carried out. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Co2 system all flexible hoses 10 year renewal to be carried out. 680L Flexible hoses - 211 ST | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 034
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/034 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Hot water hydrophore tank leacky botom shell plate to be croped & renewed. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Hot water hydrophore tank leacky botom shell plate to be croped & renewed. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 035
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/035 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Primary billge tank bottom plating corroded section (300mm X 300mm), to be cropped & renewed. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Primary billge tank bottom plating corroded section (300mm X 300mm), to be cropped & renewed. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 036
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/036 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
HFO bunker manifold both the filters to be rapaired or fabricated as per owners advice. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
HFO bunker manifold both the filters to be rapaired or fabricated as per owners advice. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 037
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/037 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Shaft bearing to be opene up inspected presented to the survey & boxed up. Clearence to be taken & recorded | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
'Shaft bearing to be opene up inspected presented to the survey & boxed up. Clearence to be taken & recorded | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 038
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/EN/038 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Windlass (STBD) hydrolic mootor slow operation to be investigated, and to be serviced accordingly. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Windlass STBD hydrolic mootor slow operation to be investigated. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date