## Sheet1
SPECIFICATION OF REPAIRS ITEMS FOR DRY DOCKING - DECK
M.V. | Ceylon Breeze |  | 08.09.2025
Job No | Description | Delegation | Delegation | Remarks
CB/DD2/DK/001 | Close up inspection and paint up gradation of all cargo holds and hatch coamings | Dock Yard | Ship Staff
CB/DD2/DK/002 | Inspection of Ballast tank valves |  | Ship Staff
CB/DD2/DK/003 | Freeing of hatch cover rollers | Dock Yard
CB/DD2/DK/004 | Overhaul of ballast and bilge eductor |  | Ship Staff
CB/DD2/DK/005 | Overhaul & Calibrate Ballast and draft gauges | Dock Yard
CB/DD2/DK/006 | Overhaul of cargo hold bilges non return valves ( 5 nos) | Dock Yard | Ship Staff
CB/DD2/DK/007 | Inspection, repair and overhauling of Provision Crane | Dock Yard
CB/DD2/DK/008 | Repaire holding base of safety line stauntions on main deck Port side and Stbd side | Dock Yard
CB/DD2/DK/009 | Gangway bottom platform rollers, rubber protection | Dock Yard
CB/DD2/DK/010 | Port side and Stbd side Windlass brake adjustment mechanism to be adjusted | Dock Yard
CB/DD2/DK/011 | Minimum of 4 nos Flood lights to bridge wings to illuminate deck | Dock Yard
CB/DD2/DK/012 | Bottom inspection, preparation and painting | Dock Yard
CB/DD2/DK/013 | Anchor Cable calibration, marking and painting | Dock Yard
CB/DD2/DK/014 | Cleaning and painting of chain lockers | Dock Yard | Ship Staff
CB/DD2/DK/015 | Inspection of hawse pipe collars of both ends | Dock Yard
CB/DD2/DK/016 | Echo sounder/Doppler logs tranduseres check and clean | Dock Yard
CB/DD2/DK/017 | Sacrifice anode in ship side (impressed current system) | Dock Yard
CB/DD2/DK/018 | Sea chest cleaning and painting | Dock Yard
CB/DD2/DK/019 | Inspection of Sea suction and discharge valves | Dock Yard
CB/DD2/DK/020 | Inspection and repair damages to the bilge keel as required | Dock Yard
CB/DD2/DK/021 | Inspection Sanitory stome valve | Dock Yard
CB/DD2/DK/022 | Overhaul and Inspection of Ballast and fuel tank air pipe vent heads |  | Ship Staff
CB/DD2/DK/023 | Load test of Accommodation and combination ladders Port & Starboard | Dock Yard
CB/DD2/DK/024 | Fire line pressure test |  | Ship Staff
CB/DD2/DK/025 | Ballast line pressure test |  | Ship Staff
CB/DD2/DK/026 | All Cargo Holds vertical & spiral ladder's Steps, hand rails and protection bars inspection, and renewed as required | Dock Yard | Ship Staff
CB/DD2/DK/027 | Overhaul of all fair lead rollers. |  | Ship Staff
CB/DD2/DK/028 | Life boat davit load test, dynamic test of winch break system, free falls releasing system | Dock Yard
CB/DD2/DK/029 | Life boat/rescue boat, suez , bunker davit and provision crane wire falls renewal | Dock Yard | Ship Staff
CB/DD2/DK/030 | Load test of the suez canal, bunker davit and provision crane | Dock Yard | Ship Staff
CB/DD2/DK/031 | Test and discharge at least one from each fire extinguisher (portable and mobile) |  | Ship Staff
CB/DD2/DK/032 | Check and tightening of sleave bearing crews/studs and check the hydralic hoses |  | Ship Staff
CB/DD2/DK/033 | Hatch covers pressure test for water tightness |  | Ship Staff
CB/DD2/DK/034 | Removing salt impurities in ballast water treatment plant | Dock Yard
CB/DD2/DK/035 | Fixed CO2 fire extinguishers system 5 year maintanance | Dock Yard
CB/DD2/DK/036 | Hatch cover opening hydrolic system piping system to be inspected and renew badly corroded pipes | Dock Yard | Ship Staff
CB/DD2/DK/037 | Hatch cover hydrolic rams leaking from seals | Dock Yard
CB/DD2/DK/038 | Port winch clutching system to aligned | Dock Yard
CB/DD2/DK/039 | Both anchor cables studs to be inspected and repaired as necessary | Dock Yard
CB/DD2/DK/040 | Freeing of hatch cover rollers | Dock Yard
CB/DD2/DK/041 | Portside Hull dent IWO Cylinder oil tank to repair | Dock Yard
CB/DD2/DK/042 | Hatch cover middle rubbers to renew |  | Ship Staff
CB/DD2/DK/043 | NO: 01 HATCH COVER FWD PORT SIDE HYDROLIC RAMP BOTTOM BEARING DAMAGE | Dock Yard
CB/DD2/DK/044 | Port side cable duct pipe joining plungers nut and bolt heavily corroded need to be renew | Dock Yard | Ship Staff
CB/DD2/DK/045 | NUMBER OF SCUPPERS (NINE-9) ARE CHOCKED AND UNABLE TO CLEAR. | Dock Yard | Ship Staff
CB/DD2/DK/046 | ALL CRANE TOP SHEAVES ASSEMBLY | Dock Yard
CB/DD2/DK/047 | JIB TOP MOUNTING SHEAVES OVERHAULING FOR 2 CRANES | Dock Yard
CB/DD2/DK/048 | BOTTOM BEARING FOR NO 03,04 | Dock Yard
CB/DD2/DK/049 | STEVERDORE WASH ROOM TO BE REFURBISHED | Dock Yard | Ship Staff
CB/DD2/DK/050 | CRANE OUTSIDE FLAT FORM WASTED AREAS TO BE CROP AND REMOVED | Dock Yard | Ship Staff
CB/DD2/DK/051 | Accomodation Hot water piping system to be repaired. Corroded pipes to be removed and fabricate accordingly. | Dock Yard | Ship Staff

## CB-DD2-DK-001
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | MV CEYLON BREEZE
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CB/DD2/DK/001 | JOB No. |  | JOB No.
Date : | 2025-06-30 |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
Class Representative
Close up inspection and paint up gradation of all cargo holds and hatch coamings. | [6 empty] | Flag Sate Representative
[6 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Close up inspection and paint up gradation of all cargo holds area for blasting and staging will be deceided after inspection by owners representative. | [6 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[6 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Staging
Crane service
HP washing, Grit blasting and painting of cargo hold bulkhead. F & A TST slope plating P & S, side shell frames P & S, Hopper Slope P & S. Lower stool space F & A, Under cross deck F & A, Hatch & beam F & A, Hatch coaming area ladders. Mucking all grits & rusts. To be painted by 2 coats of epoxy. | [6 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements | [5 empty] | Sub contract
C.H No -1; C.H No -2; C.H No -3; C.H No -4; C.H No -5
Other details
Materials
Yard supply
[6 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## CB-DD2-DK-002
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/002 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Inspection of Ballast tank valves | [5 empty] | Flag Sate Representative
Owners Representative
Manufacturers' Representative
MANUFACTURER- PLEIGER FAR EAST LLC | [5 empty] | Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
[5 empty] | x | Gas free certificate
Lighting
1. All the valves, valve Controls to be inspected by maker's technician |  |  |  |  | x | Ventilation
2. If any malfunction, same to be rectified. | [5 empty] | Cleaning before
3. After completion of inspection function test to be carried out for each valve. | [5 empty] | Cleaning after
Staging
Crane service
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Transportation internal
Transportation outside yard
Access work
VALVE ELE.REMOTE OPERATE WITH OPEN SHUT INDICATOR | [5 empty] | Corrosion protection
MANUFACTURER- PLEIGER FAR EAST LLC | [5 empty] | Galvanizing
TTL Numbers : 68 SETS | [5 empty] | Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
Other details
Duct keel , Engine room , Forecastle
Materials
Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 003
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: |  | CEYLON BREEZE
DECK |  |  | VESSEL |  | OFFICE |  | YARD
|  |  | JOB No. | CB/DD2/DK/003 | JOB No. |  | JOB No.
Date : |  |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) | [5 empty] | Inspection / Surveys
[6 empty] | x | Class Representative
Flag Sate Representative
Freeing of hatch cover rollers | [5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description | [5 empty] | Yard work to be included
Gas free certificate
Lighting
1. All the hatch cover rollers to be inspected by maker's technician | [6 empty] | Ventilation
2. If any malfunction, same to be rectified. | [6 empty] | Cleaning before
3. After completion of inspection function test to be carried out for each roller. | [6 empty] | Cleaning after
Staging
[6 empty] | x | Crane service
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [6 empty] | Transportation internal
Transportation outside yard
wheel type | hatch covers | [5 empty] | Access work
K104717 | 1-2(P) , 2-2(P) , 4-2(P) , 5-2(P) | [5 empty] | Corrosion protection
K102702 | 1-2(S) , 2-2(S) , 4-2(S) , 5-2(S) | [5 empty] | Galvanizing
K104718 | 1-3(P) , 2-3(P) , 4-3(P) , 5-3(P)
K102703 | 1-3(S) , 2-3(S) , 4-3(S), 5-3(S) | [5 empty] | Pressure testing
K104720 | 3-2(P) |  |  |  |  | x | Function testing
K102746 | 3-2(S) | [5 empty] | Non-destructive test
K104721 | 3-3(P) | [5 empty] | Correction drawings
K102747 | 3-3(S) |  |  |  |  | Sub contract
Location, material, access work, staging, other details & special requirements
Other details
SIDES OF THE HATCH COVERS
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
[6 empty] | x | Drawing
Prepared by |  |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## CB DD2 DK 004
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/004 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Flag Sate Representative
Overhaul of ballast and bilge eductor |  |  |  |  | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ballast and bilge eductors to removed and overhaul. | [5 empty] | Ventilation
Cleaning before
Cleaning after
Staging
Crane service
Transportation internal
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
01) Ballast eductor to be overhauled
02) Eductor nozzle to be inspected. | [5 empty] | Pressure testing
03) Glass flaking to be carried out if necessary. |  |  |  |  | x | Function testing
04) After boxing back inspection / Function test of valves to be carried out. | [5 empty] | Non-destructive test
Correction drawings
Manufacturer : Jiangsu Zhenhua Pump Industry Co, LTD. |  |  |  |  | Sub contract
Type : CP - 50 0.18 - 3 Nos
CP - 25 0.08 - 1 Nos
CP - 18 0.2 - 1 Nos |  |  |  |  | Other details
Location, material, access work, staging, other details & special requirements |  |  |  |  | Materials
Yard supply
E/R bottom platform - 3 Nos (50m3 * 0.18Mpa) |  |  |  |  | x | Owner’s supply
FWD Void space - 25m3 * 0.08Mpa | [5 empty] | Maker’s supply
Emergency Gen Rm - 18m3 * 0.2 Mpa
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 005
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/005 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Overhaul & Calibrate Ballast and draft gauges. | [5 empty] | Flag Sate Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
[5 empty] | x | Gas free certificate
All ballast and console to be inspected and all remote gauges to be calibrated by maker's technician. | [5 empty] | Lighting
[5 empty] | x | Ventilation
Repairing of No.3 port side and No.5 port side, which gives wrong reading at present. | [5 empty] | Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Sensor System | [5 empty] | Transportation outside yard
Manufacturer : Utsuki Keiki Co. LTD, | [5 empty] | Access work
Type : SJ-X-G | [5 empty] | Corrosion protection
Sensor - N1406GXN | [5 empty] | Galvanizing
15.03.20 | [5 empty] | Paintwork (T/Up, Full Coat)
UPX-W12P45-L | [5 empty] | Pressure testing
15XB0148 |  |  |  |  | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Draft gauages location; |  |  |  |  | Other details
FWD - Below emergency fire pump space
Mid ship - On the duct keel
AFT - Bottom platform of the engine room, near the stern tube
Ballast console in ship's office |  |  |  |  | Materials
No 01, 02, 03, 04 & 05 WBT Tanks (Port side & Stbd side , Tot 10 Nos) in Duct Keel |  |  |  |  | x | Yard supply
Fore Peak Tank | [5 empty] | Owner’s supply
Aft Peak Tank | [5 empty] | Maker’s supply
Fresh Water Tanks (Port side & Stbd Side) In Steering Gear Rm
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 006
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/006 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Overhaul of cargo hold bilges non return valves (5 cargo holds). | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
1. Open up and overhaul all the valves. Clean and two coats of primer to be applied. After completion of painting function test to be carried out. | [5 empty] | Gas free certificate
Lighting
Ventilation
2. 11 nos. of angle valves for cargo hold bilges NO. 1 to 5 (p & s) to be overhauled | [5 empty] | Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Sub contract
Other details
Location, material, access work, staging, other details & special requirements
Inside cargo holds bilges in 1,2,3,4 & 5 cargo holds |  |  |  |  | Materials
Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
[5 empty] | x | Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 007
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/007 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Flag Sate Representative
Inspection, repair and overhauling of provision crane | [5 empty] | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gear Wheel not allin with the track teeth and the gap between rollers and the track way to high. Vibration during operation. | [5 empty] | Gas free certificate
Lighting
Check and overhual all function of the crane, all limit switch, travel wheels and guide rollers | [5 empty] | Cleaning before
Cleaning after
Replace Wires and carryout load test. (2 Nos) | [5 empty] | Staging
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Crane service
[5 empty] | x | Transportation internal
Capacity : 4T (SWL) | [5 empty] | Transportation outside yard
Height of lift : 35m | [5 empty] | Access work
Hoisting speed: 10 m/min | [5 empty] | Corrosion protection
Travel speed : 8 m/min | [5 empty] | Galvanizing
Wire Rope : Dia - 13 mm | [5 empty] | Paintwork (T/Up, Full Coat)
Construction 35W * 7 , Galvanized | [5 empty] | Pressure testing
79m ( Breaking load 122 KN ) |  |  |  |  | x | Function testing
Rotation resistant - Yes | [5 empty] | Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
Other details
A-Deck ,Between galley & engine room
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Sketch
Prepared by |  |  | Approved by Manager SMT |  | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 008
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/008 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Repair holding base of safety line stauntions on main deck Port side and Stbd side | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Check and repair the all damage stauntions holding base of life line on the main deck port/stbd or shift the line line along the hatch coaming with new beacket. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | X | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Main deck Stbd side and Port side. |  |  |  |  | Other details
Stauntions base are on top of the fuel tanks. (Between Frame No 35 and Frame No 114)
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 009
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/009 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Flag Sate Representative
Gangway bottom platform rollers, rubber protection |  |  |  |  | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All Gangways and commbination ladders bottom platform rollers, rubber protection need to check and overhaul. (4 Nos) | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
[5 empty] | x | Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Combination ladders & Accomadation ladders
Other details
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 010
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/010 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Port/Stbd side Windlass brake adjustment mechanism to be adjusted. | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Windlass brake regulating screw and other parts of the mechanism to be check and adjust. | [5 empty] | Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirement |  |  |  |  | Sub contract
Forcastle deck |  |  |  |  | Other details
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  | x | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 011
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/011 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
4 nos Flood lights to bridge wings | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Proper installation with four flood lights to bridge front. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Specifications: | [5 empty] | Transportation outside yard
Flood Lighting fixture | [5 empty] | Access work
High Pressure Sodium Lamp | [5 empty] | Corrosion protection
400 W , 220V | [5 empty] | Galvanizing
IMPA Code - 791822 | [5 empty] | Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Bridge wings. |  |  |  |  | Other details
Materials
Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 012
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/012 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Bottom inspection, preparation and painting | [5 empty] | Flag Sate Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
•• Visual inspection of the underwater | [5 empty] | Lighting
• NDT (Non-Destructive Testing) methods • • Identify and mark damaged coating areas, corrosion, or pitting for repair | [5 empty] | Ventilation
• NDT (Non-Destructive Testing) methods • | [5 empty] | Cleaning before
• Identify and mark damaged coating areas, corrosion, or pitting for repair | [5 empty] | Cleaning after
Staging
Crane service
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Transportation internal
Transportation outside yard
B. Surface Preparation | [5 empty] | Access work
• High-pressure water washing (minimum 350 bar / 5000 psi) to remove: o Marine growth o Salt, sludge, loose paint, and scale • Grit or abrasive blasting to standard: o SA 2.5 (ISO 8501-1) or as specified • Spot or full blasting as required • Cleaning of surfaces to be free of dust, grease, and contaminants • Ensure adequate surface profile for coating adhesion | [5 empty] | Corrosion protection
Galvanizing
Pressure testing
Function testing
Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
Other details
C. Painting / Coating
• Application of paint/coating systems in accordance with the paint manufacturer's specifications and the shipowner's requirements • Coating types typically include: o Epoxy primer o Tie coat (if required) o Antifouling paint (self-polishing or hard type) • Application methods: o Airless spray o Brush/roller for touch-ups and difficult areas • Number of coats and DFT (Dry Film Thickness) to be confirmed per spec • Environmental controls: temperature, humidity, and dew point to be monitored and recorded • Final inspection and paint log documentation
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 013
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/013 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Anchor Cable calibration, marking and painting | [5 empty] | Flag Sate Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Annchor cables are measured , inspected and marked to ensure accurate lengthidentification and compliance. | [5 empty] | Lighting
Ventilation
Cleaning before
Cleaning after
Staging
Crane service
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Pressure testing
Function testing
Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
Other details
• Remove anchor cables lay on the dock floor / clean. Conduct visual inspection of links for: Deformation, wear, corrosion, cracks, or elongation • Perform dimensional measurements • Marking of Cable Lengths and Painting Reinstallation
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 014
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/014 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Cleaning and painting of chain lockers | [5 empty] | Flag Sate Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
The chain locker is cleaned to remove mud ,rust, and debris , then painted. | [5 empty] | Lighting
Ventilation
Cleaning before
Cleaning after
Staging
Crane service
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Transportation internal
Transportation outside yard
• Isolate and ventilate the chain locker area./ confined space entry permit and gas-free certificate are issued. • Remove all mud, seawater, rust scale, and debris manually or with suction/pumps. | [5 empty] | Access work
Corrosion protection
Galvanizing
Pressure testing
Function testing
Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 015
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/015 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Inspection of hawse pipe collars of both ends | [5 empty] | Flag Sate Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Corrosion , cracks , welds , alignment and coating. | [5 empty] | Lighting
Ventilation
Cleaning before
Cleaning after
Staging
Crane service
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Transportation internal
Transportation outside yard
• Visual inspection of hawse pipe collars at bow • Check for cracks, corrosion, pitting, erosion, and deformation. • Measurement of collar thickness and dimensions to compare with design specifications. • Inspection for secure fastening and proper alignment. • Verification of paint/coating condition and any signs of coating failure | [5 empty] | Access work
Corrosion protection
Galvanizing
Pressure testing
Function testing
Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 016
CEYLON SHIPPING CORPORATION LTD.
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/016 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Echo sounder/Doppler logs tranduseres check and clean | [5 empty] | Flag Sate Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Staging
Crane service
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Pressure testing
Function testing
Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 017
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/017 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Sacrifice anode in ship side (impressed current system) | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Need to renew all Sacrifice anodes of the vessel ( ballast tanks, ship side and rudder) after 5 years as per the manufacturer manuals. |  |  |  |  | x | Gas free certificate
Lighting
[5 empty] | x | Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Ballast Water Tanks |  |  |  |  | Other details
Ship sides
Rudder
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 018
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/018 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Sea chest cleaning and painting | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Preparatory Work • Drain and isolate sea chest from the system. • Remove gratings, strainers, and any internal fittings. • Conduct a preliminary inspection to identify damage, corrosion, or cracks. Cleaning • inspection for corrosion, cracks, or damage. Surface Preparation Painting | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 019
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/019 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Inspection of Sea suction and discharge valves | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Inspection of Sea suction and discharge valves • Isolate systems and ensure valves are not under pressure. c) Inspection: d) Overhauling: e) Pressure Testing: f) Reinstallation: Functional testing of valves after reinstallation. ' | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 020
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/020 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Inspection and repair damages to the bilge keel as required | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
a) inspection: • Visually inspect both port and starboard bilge keels upon docking and cleaning. • conduct close-up examination for: o cracks or fractures o buckling or denting o detached or loose welds o heavy corrosion or wastage • use NDT (ultrasonic thickness measurement, dye penetrant testing, etc.) where necessary to assess internal damage or cracking at weld joints. • remove marine growth and scale to bare metal in damaged areas. • crop and remove deformed or fractured sections of the bilge keel. • renew with suitable marine-grade steel plates and stiffeners as per original specifications or class-approved drawings. • ensure proper alignment and welding procedures are followed. • grind and fair welds smoothly after repair. c) welding: • all welding to be carried out by certified welders using class-approved procedures. • weld seams to be inspected visually and by ndt (as required by class). d) coating: • apply primer and anti-corrosive/anti-fouling coating as per vessel’s paint specification. • ensure surface preparation meets sa 2.5 standard or equivalent before painting. e) final inspection: • inspection of repaired areas by class surveyor and owner’s representative. • submit all required repair reports and certificates | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 021
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/021 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Inspection Sanitory stome valve | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
a) Preparation: • Isolate valve from the sanitary drainage system. • Dismantle • Inspect internal components c) Cleaning: d) Overhaul • Functionally test the valve f) Reinstallation: | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 022
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/022 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Overhaul and Inspection of Ballast and fuel tank air pipe vent heads | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Overhaul and Inspection of Ballast and fuel tank air pipe vent heads • tanks are inerted or gas-freed and marked safe for inspection. • Isolate and tag air pipe systems where necessary. Removal and Dismantling: Inspection Overhaul & Cleaning Reinstallation: • Apply protective coating as required after reinstallation. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 023
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/023 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Load test of Accommodation and combination ladders | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Need to carryout load test on Accomodation and Combinations ladders in both port side and STBD sides. 4 Nos. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Main Deck |  |  |  |  | Other details
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 024
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/024 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Fire line pressure test | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
• inspect the fire line visually for obvious damage, corrosion, or loose fittings before pressurization. • connect a calibrated pressure pump or fire pump to the fire main. c) pressure test by • gradually pressurize the fire line • maintain pressure for 10–15 minutes d) post-test: | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 025
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/025 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Ballast line pressure test | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
• ensure all tanks connected to ballast lines are empty and safe for testing. • isolate the section of ballast line to be tested. • connect a calibrated pressure pump and pressure gauge. gradually increase pressure to: as required by class • hold pressure for a minimum of 10–15 minutes. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 026
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/026 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
All Cargo Holds vertical & spiral ladder's Steps, hand rails and protection bars inspection, and renewed as required | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
In Cargo Holds vertical & spiral ladder's Steps and hand rails,protection bars are bended and damages. Need to recitified as required | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
01, 02, 03, 04 & 05 Cargo Holds |  |  |  |  | Other details
Materials
Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 027
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/027 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Overhaul of all fair lead rollers. | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 028
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/028 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Life boat davit load test, dynamic test of winch break system, free falls releasing system | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Life boat davit load test, dynamic test of winch break system, free falls releasing system | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Jiangyin Xinjiang F.R.P. Co., Ltd. | [5 empty] | Transportation internal
NO.14 NORTH STREET,YUECHENG TOWN | [5 empty] | Transportation outside yard
JIANGYIN CITY, JIANGSU PROVINCE P.R.CHINA | [5 empty] | Access work
Post Code:214404 Tel:+86 510 86581115,86581273,86585222 Fax:+86 510 86581013 E-mail: davit@jyboat.com | [5 empty] | Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
C Deck Life Boat Deck |  |  |  |  | Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 029
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/029 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Life boat/rescue boat, suez , bunker davit and provision crane wire falls renewal | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Replacing of Life boat/rescue boat, suex canal, bunker davit and provision crane wire falls. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[6 empty] | Cleaning after | Suez cannal Davit Wire Rope
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging | Diameter - 8mm
[6 empty] | Crane service | No Rotation
Life Boat Wire Rope |  | Rescue Boat, Life Raft Davit Wire Rope |  |  |  | Transportation internal | Construction 19 * 7 , Galvanized
Dia - 20mm |  | Dia - 16mm |  |  |  | Transportation outside yard | Length - 15m
Length - 85m |  | Length - 35m |  |  |  | Access work | Bunker Davits Wire Rope
Breaking Load - 250 KN |  | Breaking Load - 170 KN |  |  |  | Corrosion protection | Diameter - 8mm
Corrosion Resistant |  | Corrosion Resistant |  |  |  | Galvanizing | No Rotation
Rotation Resistant |  | Rotation Resistant |  |  |  | Paintwork (T/Up, Full Coat) | Construction 19 * 7 , Galvanized
Construction - 18 x 19S + SF |  | Construction - 18 x 19S + SF |  |  |  | Pressure testing | Length - 25m
|  | One end pressed thimble JIS type (Mechanical splice) |  |  |  | Function testing | Provision Crane Wire Rope
[6 empty] | Non-destructive test | Diameter - 13 mm
[6 empty] | Correction drawings | Construction 35W * 7 , Galvanized
79m ( Breaking load 122 KN )
Rotation resistant - Yes
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
C Deck Life Boat Deck |  |  |  |  | Other details
A Deck Stbd Side
Fox'le deck
Mian deck infront of accommodation port and stbd.
Materials
Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 030
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/030 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Load test of the davits | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Load test of the suez canal, bunker davits and provision crane | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Sub contract
Location, material, access work, staging, other details & special requirements
[5 empty] | Other details |  | BUNKER DAVIT LOAD TEST | SUEZ CANNAL DAVIT LOAD TEST
Main Deck
Forecastle
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 031
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/031 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Test and discharge at least one from each fire extinguisher (portable and mobile) | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 032
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/032 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Check and tightening of sleave bearing crews/studs and check the hydralic hoses | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 033
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/033 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Hatch covers pressure test for water tightness | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
all hach covers on completion of replacing middle hatch rubber should be water tesed | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 034
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/034 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Removing salt impurities in ballast water treatment plant | [5 empty] | Flag State Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Engine Room |  |  |  |  | Other details
Materials
Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 035
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/035 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Fixed CO2 fire extinguishers system 5 year maintanance | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Upper Deck CO2 Room - 45kg - 211 btls |  |  |  |  | Other details
2 Bottles infront of Engine control room - 45 kg - 2 btls
Gally - 7 kg - 1 blt
Materials
[5 empty] | x | Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 036
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/036 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Hatch cover opening hydrolic system piping system to be inspected and renew badly corroded pipes | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 037
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/037 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Hatch cover hydrolic rams leaking from seals | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 038
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/038 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Port winch clutching system to aligned | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 039
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/039 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Both anchor cables studs to be inspected and repaired as necessary | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 040
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/040 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Freeing of hatch cover rollers ( 4 nos frozen ) | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 041
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/041 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Portside Hull dent IWO Cylinder oil tank to repair | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 042
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/042 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Hatch cover middle rubbers to renew in CH No 1 ,2,3,4,5 | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Removal of middle hatch cover WT rubber and replacement | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 043
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/043 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
NO: 01 HATCH COVER FWD PORT SIDE HYDROLIC RAMP BOTTOM BEARING DAMAGE | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 044
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/044 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Port side pipe cable duct pipe joining plungers nut and bolt heavily corroded need to be renew | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
[5 empty] | x | Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 045
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/045 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
NUMBER OF SCUPPERS (NINE-9) ARE CHOCKED AND UNABLE TO CLEAR. | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
[6 empty] | Gas free certificate |  | F'CASTLE PORT |  | BRIDGE DECK PORT |  | BRIDGE DECK STBD
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
[6 empty] | Non-destructive test | A DECK AFT PORT SIDE AND TOP OF EM'GEN |  | A DECK AFT STBD SIDE AND TOP OF ELECTRIC STORE |  |  | A DECK STBD SIDE
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
[5 empty] | x | Photograph | POOP DECK PORT STBD SIDE |  |  |  | POOP DECK STBD SIDE AFT SCUPPER
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 046
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/046 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
ALL CRANE TOP SHEAVES ASSEMBLY | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 047
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/047 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
JIB TOP MOUNTING SHEAVES OVERHAULING FOR 2 CRANES | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 048
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/048 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
OVERHAUL BOTTOM BEARINGS FOR NO 03 , 04 CRANES | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  | x | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 049
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/049 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
STEVERDORE WASH ROOM TO BE REFURBISHED | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 050
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/050 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
CRANE OUTSIDE FLAT FORM WASTED AREAS TO BE CROP AND REMOVED | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date

## CB DD2 DK 051
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
DECK |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD2/DK/051 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Accomodation Hot water piping system to be repaired. Corroded pipes to be removed and fabricate accordingly. | [5 empty] | Flag State Representative
Owners Representative
Manufacturers' Representative
Underwriters
[5 empty] | S | Others
Actual Job description |  |  |  |  | Yard work to be included
• Inspect hot water lines and identify damaged/corroded sections. • Isolate, drain, and remove defective pipes. • Fabricate and install new pipe sections as per specifications. • Conduct pressure testing to ensure leak-free installation. • Restore system and verify operational integrity. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
H.W.PIPE : O.D./THK/LENGTH- 45 *2MM/50M O.D./THK/LENGTH- 38 *2MM/60M O.D./THK/LENGTH- 32 *2MM/30M O.D./THK/LENGTH- 25 *2MM/20M O.D./THK/LENGTH- 22 *2MM/60M | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special requirements |  |  |  |  | Sub contract
Required pipes are available on board |  |  |  |  | Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by ; |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  | Name, Signature & date