## Index
SPECIFICATION OF REPAIRS (DOCKING) - (INDEX- Engine)
M.V. | Ceylon Princess |  |  | Date: | 2020-09-10
Job No | Description | Delegation | Requisition No | Reqn Status | Remarks
EN/001 | All sea suction and overboard valves.
EN/002 | Stern tube seals and chrome liner inspection.
EN/003 | Propeller inspection
EN/004 | Rudder and rudder carrier bearing inspection
EN/005 | Boiler internal and external inspection and survey
EN/006 | Main engine all units main bearings, cross head bearings and bottom end bearings inspection and survey
EN/007 | All air bottle survey
EN/008 | Main engine turbocharger overhaul.
EN/009 | All auxiliary engine governor overhaul
EN/010 | Bunker davit modification to be done
EN/011 | All three main S.W Pump discharge pipe line elbow renewal.
EN/012 | All main S.W Pump discharge butterfly valves to replaced with NR valves
EN/013 | Main Engine all five unit fuel oil pressure boosters to be overhauled
EN/014 | Renewal of RO Plant piping
EN/015 | Isolation valve to be fitted to FWG Suction line from Main Pipe.
EN/016 | LT Cooler in/out SW connections to renew
EN/017 | BWMS modification to suit with actual capacity.
EN/018 | Higher capacity sludge pump to be installed
EN/019 | Main Engine air cooler to be cleaned
EN/020 | Boiler Dump condensor (Atmos condenser) to be cleaned
EN/021 | All ER coolers to be cleaned
EN/022 | ME Thrust bearing to be inspected and clearence to check
EN/023 | Waste oil tank extractor fan and air bubbling arrangement to be fitted
EN/024 | Galley AC to be repaired
EN/025 | Drain Holes to be cut in Hull side plates(Stiffeners) allowing water to drain in to bilges.
EN/026 | Provision crane modification to be done
EN/027 | Deck Crane Inspection & Maintenance.
EN/028 | FWG Ejector pump discharge SW line to fabricate and fix
EN/029 | RO Plant SW pump suction line modification
EN/030 | CSM items - ME pumps survey
EN/031 | OWS 15PPM alarm monitoring unit calibration.
EN/032 | AE no 2 shaft seal to replace with a new one(Rectify the oil leake from the shaft seal)
EN/033 | LT cooler capacity to be increased(add extra plates)
EL/001 | All Deck crane main motors and hydraulic cooler motors to be serviced and bearing replaced
EL/002 | All engine room blower motors to be serviced and bearing replaced
EL/003 | All generator alternators to be serviced.
EL/004 | Main switch board to be serviced and all Meters to be callibrated
EL/005 | Emergency switch board to be serviced and all Meters to be callibrated
EL/006 | Main engine control system and alarm panel of Kongsberg to be serviced and callibrated.
EL/007 | Main engine MAN B&W control system to be callibrated and serviced
EL/008 | All tanks sounding/tempreture sensors of Ballst Control System to be serviced, repaired and callibrated.
EL/009 | ICCP System dry Dock routine to be carried out.
EL/010 | MGPS System dry Dock routine to be carried out.
EL/011 | Load test of all Deck cranes
EL/012 | Steering gear motors to be serviced and bearings to be replaced
EL/013 | M/E Auxiliary blowers to be serviced
EL/014 | LT cooling pump motors to be serviced
EL/015 | Fire & GS pump motors to be serviced
EL/016 | Bilge & GS pump motors to be serviced
EL/017 | Main Air Compressor motors to be serviced
EL/018 | Ballast pump motors to be serviced
EL/019 | Main SW cooling pump motors to be serviced
EL/020 | Shore calibration of calibrates.
Note: REPAIR SPECIFICATION NUMBERING TO CONTINUE AS FOLLOWS:
DECK / RADIO DEPARTMENT: D-001 ～D-999
ENGINE / ELECTRICAL DEPARTMENT: E-001 ～E-999

## EN 001
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/001 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
All sea suction and overboard valves. Valve Specifications details attached in annex 1 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All sea suction and overboard valves to be removed, lapped or renewed as per the condition, pressure tested and assembled back(If valve gards are there those has to be cleaned and panted). | [5 empty] | Gas free certificate
Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
1) The valves mentioned in the attached list to be cleaned overhauled |  |  |  |  | x | Transportation internal
and surveyed by class surveyor. | [5 empty] | Transportation outside yard
2) Butterfly valve seat rings to renew/repair rubber line if found | [5 empty] | Access work
defective. Fitting bolts and nuts to renew if required. | [5 empty] | Corrosion protection
4) Valve operating gear and indicators to be included in the overhaul of | [5 empty] | Galvanizing
the valves. Job will be considered as complete subject to holding of | [5 empty] | Paintwork (T/Up, Full Coat)
both valve and the connecting flange and no leakage from any joint | [5 empty] | Pressure testing
during dock floating. | [5 empty] | Function testing
Non-destructive test
Valve Specifications details attached in annex 1 | [5 empty] | Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Valve location details attached in annex 1
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## Annex 1
| Valve | System | DN | Valve Type | Name on plate | Location | Dimentions on Drwg (MPa) | Dimentions from local check (bar)
Overboard Discharge Valves
1 | Ballast Pump 1 to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN350 | Butterfly V. | BWV09 | E/R | 1DN350 | 10DN350
2 | Ballast Pump 2 to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN350 | Butterfly V. | BWV10 | E/R | 1DN351 | 10DN350
3 | Ballast Stipp. Eductor Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN150 | Stop Check v. | BWV16 | E/R | 0.6DN150 | 6DN150
4 | Bilge Eductor for C/H Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN125 | Stop Check v. | BGV27 | E/R | 0.6DN125 | 6DN125
5 | Main Bilge Pump to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN250 | Stop Check v. | BGV13 | E/R | 0.6DN250 | 6DN250
6 | Oily Bilge Water Sepatrator to OVBD | E/R Oily Water Separating System | DN40 | Stop Check v. | OWV04 | E/R | 0.6DN50 | 25DN50
7 | Sewage Discharge OVBD | Sewage Treatment Plant system | DN150 | Storm Vv | SWV01 | E/R | 0.6DN150 | 5DN150
8 | Ref. chamber Discharge OVBD | Layout of Sanitary Drain Piping (Grey water) | DN100 | Stop Check v. | GPV01 | E/R | 2.5DN100 | 25DN100
9 | Sea Water Cooling Pump to OVBD | Cooling Sea Water System | DN300 | Stop Check v. | CSV19 | E/R | 0.5DN300 | 10DN300
10 | Fresh water Generator Sea Water outlet OVBD | Cooling Sea Water System | DN80 | Stop Check v. | CSV20 | E/R | 0.5DN80 | 25DN80
11 | Boiler Blow to OVBD | Feed Water System | DN40 | Boiler Side Drain V. | FEV08 | E/R | 2.5DN32 | 25DN40
13 | BWTS Back Flushing to OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN125 | Butterfly V. | BWV34 | E/R | 1DN125 | 10DN125
14 | F.P. TK. Ballast water Overflow to OVBD (P) | Ship's Air, Sounding and Filling Pipes | DN300 | Stop Check v. | AVV101 | Fwd below Boatswain store | 0.6DN300 | 10DN300
15 | F.P.TK. Ballast Water Overflow to OVBD (S) | Ship's Air, Sounding and Filling Pipes | DN300 | Stop Check v. | AVV102 | Fwd below Boatswain store | 0.6DN300 | 10DN300
16 | AFT. Mooring winch Cooling Water to OVBD | Hydraulic diagram of Mooring Winch | DN50 | Stop Check v. | FFV244 | S.G Room |  | 25DN50
17 | Bilge Eductor for C/L Discharge OVBD | Bilge, Ballast & Fire Fighting System In E/R | DN80 | Stop Check v. | BGV130 | Fwd below Boatswain store | 0.6DN80 | 25DN80
Sea Suction Valves
18 | Low Sea Suction | Bilge, Ballast & Fire Fighting System In E/R | DN500 | Remote Controled Butterfly Valve Flanged | CSV24 | E/R | 1DN500 | 6DN500
19 | Low Sea Chest Air Vent | Bilge, Ballast & Fire Fighting System In E/R | DN50 | Stop Valve(Bronze) | CSV22 | E/R | 2.5DN50 | 25DN50
20 | Low Sea Chest Steam blow | E/R Steam System |  | Stop Valve | STV24 | E/R | 2.5DN15 | 25DN20
21 | From Central FW Cooler | Bilge, Ballast & Fire Fighting System In E/R | DN200 | Stop Check Valve | CSV21 | E/R | 0.6DN200 | 10DN200
22 | High Sea Suction | Bilge, Ballast & Fire Fighting System In E/R | DN500 | Remote Controled Butterfly Valve Flanged | CSV25 | E/R | 1DN500 | 6DN500
23 | High Sea Chest Air Vent | Bilge, Ballast & Fire Fighting System In E/R | DN50 | Stop Valve(Bronze) | CSV23 | E/R | 2.5DN50 | 25DN50
24 | High Sea Chest Steam blow | E/R Steam System |  | Stop Valve | STV25 | E/R | 2.5DN15 | 25DN20
25 | Emergency F.P Suction Valve | Emergency Fire Pump Room | DN125 |  | EFV01 | E.F.P Room | 0.4DN125 | 4DN125
26 | E.F.P Sea suction Air pipe | Emergency Fire Pump Room | DN65 | Stop Valve | EFV03 | E.F.P Room | 2.5DN65 | 25DN65
27 | Compressed air blow for sea chest | Emergency Fire Pump Room | DN20 | Stop Valve | EFV04 | E.F.P Room | 2.5DN20 | 25DN20
28 | Aft Draft Sensor Inlet | Aft Draft Sensor Inlet | DN40 | Globe valve |  | E/R | DN40 | 25DN40
29 | Mid Draft (P) Sensor inlet | Mid Draft (P) Sensor inlet | DN65 | Stop Valve |  | pipe tunnel | DN65 | 16DN25
30 | Mid Draft (S) Sensor inlet | Mid Draft (S) Sensor inlet | DN65 | Stop Valve |  | pipe tunnel | DN65 | 16DN25
31 | FWD Draft Sensor inlet | FWD Draft Sensor inlet | DN25 | Globe valve |  | E.F.P Room | DN25 | 25DN25

## EN 002
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD | AFT SEAL
|  | JOB No. | CP/DD1/EN/002 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Stern tube AFT seals replacement and inspection of the FWD seals and chrome liner. Type : STERNGUARD OLS4-P / OLS2-P Maker: Wartsila Japan Ltd., Toyama Factory, Japan | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Stern tube AFT seals replacement and chrome liner and FWD seals inspection to be carried out and renew if required. | [5 empty] | Gas free certificate
renewal or repair as per the condition. | [5 empty] | Lighting
AFT seals replacement to be followed as per Operation Manual
instruction procedure.- 3.4 Preparation for installation and
3.5 Installation. | [5 empty] | Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Type : STERNGUARD OLS4-P / OLS2-P Maker: Wartsila Japan Ltd., Toyama Factory, Japan | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
FWD SEAL

## EN 003
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/003 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Propeller inspection Specification details attached | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
1) To clean propeller 2) To carry out propeller polishing 3) To carry out dye penetrant test for cracks 1) To clean propeller 2) To carry out propeller polishing 3) To carry out dye penetrant test for cracks | [5 empty] | Gas free certificate
2) To carry out propeller polishing 3) To carry out dye penetrant test for cracks | [5 empty] | Lighting
3) To carry out dye penetrant test for cracks | [5 empty] | Ventilation
Propeller inspection, pull-down and push-up as per condition. |  |  |  |  | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
[5 empty] | x | Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 004
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/004 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Rudder and rudder carrier bearing inspection Specification details attached | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Rudder and rudder carrier bearing inspection and repair as per the condition | [5 empty] | Gas free certificate
condition. | [5 empty] | Lighting
1. Rudder jumping clearances to be recorded.
2. Bottom plug to remove and water ingress to check and rudder to
be pressure tested with compressed air.After test fill ASPHALTUM | [5 empty] | Ventilation
into rudder. |  |  |  |  | x | Cleaning before
3. Rudder surface to be inspected and checked for cracks, corrosion & cavitations.
4. Top and bottom access plates for the pintle nuts to be removed
5. Clearance of the neck bush and the rudder pintle bush measured
and recorded.
6. The cavitated areas on the rudder and horn to be repaired by 11. The cavitated areas on the rudder and horn to be repaired by welding or cold repair
welding or cold repair as agreed with owner’s representative and
class surveyor.
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
[5 empty] | x | Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 005
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/005 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Boiler internal and external inspection and survey | [5 empty] | Flag Sate Representative
Maker: SAACKE Composite Marine Boiler CMB-VS |  |  |  |  | x | Owners Representative
Order no : N143836/2CN Serial : B2-1723 | [5 empty] | Manufacturers' Representative
Dry weight=19600kg | [5 empty] | Underwriters
Water volume=12.0 m3 | [5 empty] | Others
Operating pressure = 6.0 bar
Actual Job description |  |  |  |  | Yard work to be included
Boiler open up, internal and external inspection of fire side, water side and combustion chamber, repair as per condition. | [5 empty] | Gas free certificate
Lighting
Boiler Survey | [5 empty] | Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
SAACKE Composite Marine Boiler CMB-VS | [5 empty] | Transportation internal
Transportation outside yard
Serial : B2-1723 | [5 empty] | Access work
Order no : N143836/2CN | [5 empty] | Corrosion protection
Dry weight=19600kg | [5 empty] | Galvanizing
Water volume=12.0 m3 | [5 empty] | Paintwork (T/Up, Full Coat)
Operating pressure = 6.0 bar |  |  |  |  | x | Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 006
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/006 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Main engine selected units(as per surveyor request) main bearings, cross head bearings and bottom end bearings inspection and survey | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Type: MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Manufacturers' Representative
Serial No : JMT60-0212 | [5 empty] | Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main engine selected units(as per surveyor request) main bearings, cross head bearings and bottom end bearings open up for inspection and survey and assemble back | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
Yard supply
Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 007
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/007 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
All air bottle survey | [5 empty] | Flag Sate Representative
2 Starting air bottles - Type: A5.0-3.0 Vol: 5m3, Press: 3MPa |  |  |  |  | x | Owners Representative
Control air - Type:A0.25-0.7 Vol:0.25m3, Press: 0.7MPa | [5 empty] | Manufacturers' Representative
Emergency air - Type: A0.25-3.0 Vol: 0.25m3, Press: 3MPa | [5 empty] | Underwriters
Service air - Type: A1.5-0.7 Vol: 1.5m3, Press: 0.7MPa | [5 empty] | Others
.
Maker: Jiangsu Yongtai Pressure Vessel CO.LTD
Actual Job description |  |  |  |  | Yard work to be included
All air bottles open up for inspection and survey | [5 empty] | Gas free certificate
All Air bottle relief valves to be calibrated | [5 empty] | Lighting
All Air compressor relief valves to be calibrated | [5 empty] | Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
2 Starting air bottles - Type: A5.0-3.0 Vol: 5m3, Press: 3MPa | [5 empty] | Transportation internal
Control air - Type:A0.25-0.7 Vol:0.25m3, Press: 0.7MPa | [5 empty] | Transportation outside yard
Emergency air - Type: A0.25-3.0 Vol: 0.25m3, Press: 3MPa | [5 empty] | Access work
Service air - Type: A1.5-0.7 Vol: 1.5m3, Press: 0.7MPa | [5 empty] | Corrosion protection
. | [5 empty] | Galvanizing
Maker: Jiangsu Yongtai Pressure Vessel CO.LTD | [5 empty] | Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 008
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/008 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Main engine turbocharger overhaul. | [5 empty] | Flag Sate Representative
MAN Diesel & Turbo |  |  |  |  | x | Owners Representative
Type: TCA55-21246 | [5 empty] | Manufacturers' Representative
Year :2014 | [5 empty] | Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main engine turbocharger overhaul to be carried out | [5 empty] | Gas free certificate
Turbocharger to be dismantled by shore staff. | [5 empty] | Lighting
Rotor will transported to shore workshop for cleaning and balancing
and return back to ship.
All consumables to be renewed.
Turbocharger assembled in place and all clearances to be taken and | [5 empty] | Ventilation
recorded. |  |  |  |  | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN Diesel & Turbo |  |  |  |  | x | Transportation internal
Type: TCA55-21246 | [5 empty] | Transportation outside yard
Year :2014 | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 009
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/009 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All auxiliary engine governor overhaul Model : ZEXEL Governor model RHD6 Serial No: Gen 1 - 30204003, Gen 2 - 45629006, Gen 3 - 45629004 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All three auxiliary engine governors to be overhauled | [5 empty] | Gas free certificate
Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
ZEXEL Governor model RHD6 | [5 empty] | Transportation internal
Serial No: Gen 1 - 30204003, Gen 2 - 45629006, Gen 3 - 45629004 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 010
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/010 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Bunker davit modification to be done | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Bunker davit hoisting gear to be connected to a pneumatic (air) motor with air hose connection instead of exsisting hand operated system | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 011
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD | Sea water pump discharge line elbow
|  | JOB No. | CP/DD1/EN/011 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All three main S.W Pump discharge pipe line elbows renewal. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All three main S.W Pump discharge elbows between pump and pump discharge butterfly valves to be renewed. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
275 mm
D= 400 mm
380 mm
650 mm
PCD = 350 mm, 12 Holes
PCD = 345 mm, 12 Holes
385 mm
Seamless Steel (Galvanized)
9.5mm thickness

## EN 012
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/012 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All main S.W Pump discharge butterfly valves to be replaced with NR valves New Valve IMPA order no- 755310, Globe valve (non return), DN350, straight type, Cast steel, pressure rating- PN16 x 3 valves | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All three main S.W Pump discharge butterfly valves to be replaced with non return valves | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Valve IMPA order no- 755310, Globe valve (non return), DN350, straight type, Cast steel, pressure rating- PN16 x 3 valves | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 013
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/013 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine all five unit fuel oil pressure boosters ( Fuel pump) to be overhauled MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine all five unit fuel oil pressure boosters to be overhauled | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 014
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/014 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Renewal of RO Plant piping. New Pipe length required- 27m, bends-15, pipe OD - 42 mm | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Renewal of RO Plant low pressure pump suction and discharge piping from sea suction valve to the RO plant | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Pipe length required- 27m, bends-15, pipe OD - 42 mm | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 015
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/015 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Interconnecting valve to be fitted to FWG Suction line from main sw pipe. New Valve Dimensions : Interconnecting valve IMPA order No 752203, Butterfly valve, wafer type nominal size-80, pipe dia. 80mm, L-46mm, H-86mm | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Interconnecting valve to be fitted to FWG Ejector pump suction line from main sw pipe. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
New Valve Dimensions : Interconnecting valve IMPA order No 752203, Butterfly valve, wafer type nominal size-80, pipe dia. 80mm, L-46mm, H-86mm | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 016
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/016 | JOB No. |  | JOB No.
Date : |  | Account Number |  |  |  |  | Sea Water In (2 pipes for 2 LT Coolers)
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
LT cooler sea water inlet and outlet pipes to be renewed | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
LT cooler No1 and No2 sea water inlet and outlet pipes ( total 4 pieces) which are ungalvanized sacrificer pipes of the LT coolers to be renewed with Zn sacrificing anodes fitted | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
[6 empty] | Access work | Sea Water Out (2 pipes with different lengths for 2 LT coolers)
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Total length
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
OD= 285 mm
OD= 375 mm
190 mm
PCD = 240mm, 8 Holes
PCD = 336 mm, 12 Holes
285 mm
285 mm
OD= 280 mm, 8 holes
PCD = 240mm
Port side total length= 165 mm
Stbd side total length= 185 mm

## EN 017
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/017 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
BWMS modification to suit with actual capacity. | [5 empty] | Flag Sate Representative
OceanGuard Ballast Water Management System BWMS Model: HMT-1000 |  |  |  |  | x | Owners Representative
Maker : HEADWAY TECHNOLOGY CO.LTD |  |  |  |  | x | Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
BWMS modification to be carried out to suit with actual capacity which is 1800 m3 per hour with both ballast pumps running. Current exsisting BWMS capacity is 1000m3 per hour. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
OceanGuard Ballast Water Management System BWMS Model: HMT-1000 | [5 empty] | Transportation internal
Transportation outside yard
Maker : HEADWAY TECHNOLOGY CO.LTD | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 018
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/018 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Higher capacity sludge pump and compatible motor to be installed Exsisting sludge pump details- Type: Mono type Discharge P : 0.35MPa, Suction P : - 0.05 MPa , Capacity : 5 m3/h , power : 2.2 Kw Exsisting pipeline details- Diameter : 75 mm x length : 65 m Flange size : OD- 160mm, PCD- 130 mm x 22 flanges | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Higher capacity sludge pump (15m3 per hour capacity) to be installed in place of the exsisting sludge pump (5m3 per hour capacity) to the exsisting system | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Exsisting sludge pump details- Type: Mono type Discharge P : 0.35MPa, Suction P : - 0.05 MPa , Capacity : 5 m3/h | [5 empty] | Transportation internal
Transportation outside yard
Access work
Exsisting pipeline details- Diameter : 75 mm x length : 65 m | [5 empty] | Corrosion protection
Flange size : OD- 160mm, PCD- 130 mm x 22 flanges | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 019
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/019 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Engine air cooler to be cleaned MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine air cooler to be cleaned | [5 empty] | Gas free certificate
Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 020
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/020 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Boiler Dump condensor (Atmos condenser) to be cleaned Maker : Taixing Navigation Machinery Factory Product No : 151594 Type : TRJ2.0/20 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Boiler Dump condensor (Atmos condenser) to be cleaned & pressure test | [5 empty] | Gas free certificate
Lighting
Ventilation
[5 empty] | x | Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker : Taixing Navigation Machinery Factory | [5 empty] | Transportation internal
Type : TRJ2.0/20 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 021
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD | No 1 Central LT Cooler
|  | JOB No. | CP/DD1/EN/021 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All engine room coolers to be cleaned Maker: TRANTER Heat Exchangers (Beijing) Co. Ltd | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All engine room coolers to be cleaned including both LT coolers, main engine jacket and LO cooler, aux engine jacket and LO coolers | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker: TRANTER Heat Exchangers (Beijing) Co. Ltd | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
No 2 LT Cooler
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
Main L.O Cooler
Jacket Water Cooler
AE Lube Oil Cooler

## EN 022
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/022 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Thrust bearing to be inspected and clearence to check MAN-B&W 5S60ME-C8.2 (Tier II) Serial No : JMT60-0212 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Thrust bearing to be inspected and clearence to check | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation internal
Serial No : JMT60-0212 | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 023
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/023 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Waste oil tank extractor fan and air bubbling arrangement to be fitted | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Extractor fan and air bubbling arrangement to be fitted on top of waste oil tank and connected to the exsisting vent line which leads to the mist box | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 024
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/ EN/024 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Galley AC to be repaired Model : USF5JA (100% Fresh Air) Maker : DAIKIN MR ENGINEERING CO. LTD | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Galley AC pressure testing and function testing of the unit to be carried out. Outer body plates and air suction filter brackets to be renewed. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Model : USF5JA (100% Fresh Air) Maker : DAIKIN MR ENGINEERING CO. LTD | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
[5 empty] | x | Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 025
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/025 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Drain Holes to be cut in ER lower deck shipside plates (Stiffeners) allowing water to drain in to bilges. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Drain Holes to be cut in ER lower deck shipside plates (Stiffeners) allowing water to drain in to bilges. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 026
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/026 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Provision crane inspections to be done Maker : Jiangyin Concrane Equipment CO.LTD Type : C4PC Serial : C4PC 15WA SWL: 4 T | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Provision crane wheel clearances to be taken and worn bushes to be replaced. Gear box to be inspected. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker : Jiangyin Concrane Equipment CO.LTD Type : C4PC | [5 empty] | Transportation internal
Transportation outside yard
Serial : C4PC 15WA | [5 empty] | Access work
SWL: 4 T | [5 empty] | Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 027
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/027 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Deck Crane No 1,2,3 & 4 Jib foot and Sheave Bearings to be inspected and replaced where neccessary. All Crane rocking tests and Load tests to be carried out. Macgregor Crane Type: GLB3030-2/2430gr | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Deck Crane No 1,2,3 & 4 Jib foot and Sheave Bearings to be inspected and replaced where neccessary. All Crane rocking tests and Load tests to be carried out. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Macgregor Crane | [5 empty] | Transportation internal
Type: GLB3030-2/2430gr | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 028
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/028 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Fresh water generator ejector pump SW discharge line renewal. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Fresh water generator ejector pump SW discharge line renewal. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
F.W. GEN. SEA WATER EJEC. PUMP DISCHARGE LINE
178
200
16X4X146
175
20
14X8X155
196

## EN 029
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/029 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
RO Plant SW pump inlet line renewal. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
RO Plant SW pump inlet line renewal. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Specification details attached | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 030
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/030 | JOB No. |  | JOB No.
Date : |  | Account Number |  |  |  |  | LO Pump
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[6 empty] | Class Representative | Type : | Deep well type Centrifugal Pump
CSM Items : No 1 and No 2 M/E LO Pumps, No 2 M/E Jacket water pump, No 1, No 2 and No 3 LT cooling pumps, No 1 and No 3 Main Sea water pumps | [5 empty] | Flag Sate Representative | Discharge Pressure : |  | 0.45 MPa
[5 empty] | x | Owners Representative | Suction Pressure : |  | 0 Mpa
[6 empty] | Manufacturers' Representative | Capacity : | 270 m3/h
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included |  | ME Jacket Water pump
CSM Items : No 1 and No 2 M/E LO Pumps, No 2 M/E Jacket water pump, No 1, No 2 and No 3 LT cooling pumps, No 1 and No 3 Main Sea water pumps | [5 empty] | Gas free certificate
[6 empty] | Lighting | Type : | Centrifugal Pump
[6 empty] | Ventilation | Discharge Pressure : |  | 0.30 Mpa
[6 empty] | Cleaning before | Suction Pressure : |  | 0 Mpa
[6 empty] | Cleaning after | Capacity : | 100 m3/h
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
[6 empty] | Transportation internal | LT Cooling FW Pump
Transportation outside yard
[6 empty] | Access work | Type : | Centrifugal Pump
[6 empty] | Corrosion protection | Discharge Pressure : |  | 0.35 Mpa
[6 empty] | Galvanizing | Suction head : |  | 0 Mpa
[6 empty] | Paintwork (T/Up, Full Coat) | Capacity : | 290 m3/h
Pressure testing
[5 empty] | x | Function testing
[6 empty] | Non-destructive test | Cooling S.W. Pump
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract |  | Type : | Centrifugal Pump
[7 empty] | Discharge Pressure : |  | 0.25 Mpa
[7 empty] | Suction head : |  | 0 Mpa
[5 empty] | Other details |  | Capacity : | 320 m3/h
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 031
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/031 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
"OWS 15 PPM BILGE ALARM (OIL CONCENTRATION DETECTOR) SHORE CALIBERATION MAKE: FELLOW KOGYO CO.,LTD Model: FOCAS-1800 Serial No : Z 4757" | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
OWS 15PPM bilge alarm(OIL concentration detector) calibrated and certificate to be issued | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Location: engine room bottom platform port side near OWS | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EN 032
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EN/032 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Aux engine no 2 Flywheel side shaft seal to be replaced. Maker: Anquing CSSC Diesel Engine Co. Ltd Model: DAIHATSU 6DK-20 Engine No: A06K 201404 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
[5 empty] | x | Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Aux engine no 2 Flywheel side shaft seal to be replaced. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
As per attached drawings | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date
Shaft seal cover
Shaft seal attached here
Shaft Seal
Shaft Seal
Fly wheel

## EN 033
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD | Central LT Cooler
|  | JOB No. | CP/DD1/EN/033 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Both LT Cooler capacity to be increased by adding 10 plates each. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Both LT Cooler capacity to be increased by adding 10 plates each. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker: TRANTER Heat Exchangers (Beijing) Co. Ltd | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 001
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/001 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All Deck crane main motors and hydraulic cooler motors to be serviced and bearing replaced (4 Deck Crane Motors) | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Macgregor Crane | [5 empty] | Manufacturers' Representative
Type: GLB3030-2/2430gr | [5 empty] | Underwriters
Main motor make: Siemens LTD, China 440V/60Hz 203kW | [5 empty] | Others
Actual Job description |  |  |  |  | Yard work to be included
All crane main motors and hydraulic cooler motors to be serviced and bearing replaced | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Macgregor Crane | [5 empty] | Transportation internal
Type: GLB3030-2/2430gr |  |  |  |  | x | Transportation outside yard
Access work
Main motor make: Siemens LTD, China | [5 empty] | Corrosion protection
Bearing : DE-6319 C3 NDE: 7319 AC | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 002
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/002 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All engine room blower motors to be serviced and bearing replaced | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Motor type; Y180L-4-H, 440V/60Hz, 22kW, 1770 rpm | [5 empty] | Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All engine room blower motors to be serviced and bearing replaced | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) |  |  |  |  | x | Staging
Crane service
Transportation internal
Motor type; Y180L-4-H, 440V/60Hz, 22kW, 1770 rpm |  |  |  |  | x | Transportation outside yard
Bearing : DE & NDE 6311 Z | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 003
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/003 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All generator alternators to be serviced | [5 empty] | Flag Sate Representative
CM-Hyaundai Three phase Brushless Synchronus Alternators |  |  |  |  | x | Owners Representative
Type: HFC6 504-14k | [5 empty] | Manufacturers' Representative
Rated output :450V/60Hz, 875kVA | [5 empty] | Underwriters
Rated Speed :720r/min | [5 empty] | Others
Actual Job description |  |  |  |  | Yard work to be included
All generator alternators to be serviced | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
CM-Hyaundai Three phase Brushless Synchronus Alternators | [5 empty] | Transportation internal
Type: HFC6 504-14k | [5 empty] | Transportation outside yard
Rated output :450V/60Hz, 875kVA | [5 empty] | Access work
Rated Speed :720r/min | [5 empty] | Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 004
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/004 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main switch board to be serviced and all Meters to be callibrated | [5 empty] | Flag Sate Representative
SaierNico Marine Switch board Maker: Zhenjiang Saiernico Electric Co. LTD |  |  |  |  | x | Owners Representative
Type : JZB-700x3/14 | [5 empty] | Manufacturers' Representative
Gen. power: 700kWx3 | [5 empty] | Underwriters
Volt: AC 450 V / 230V | [5 empty] | Others
Frequancy : 60Hz
Actual Job description |  |  |  |  | Yard work to be included
Main switch board to be serviced and all Meters to be callibrated | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
SaierNico Marine Switch board | [5 empty] | Transportation outside yard
Type : JZB-700x3/14 | [5 empty] | Access work
Gen. power: 700kWx3 | [5 empty] | Corrosion protection
Volt: AC 450 V / 230V | [5 empty] | Galvanizing
Frequancy : 60Hz | [5 empty] | Paintwork (T/Up, Full Coat)
Maker: Zhenjiang Saiernico Electric Co. LTD | [5 empty] | Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 005
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/005 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Emergency switch board to be serviced and all Meters to be callibrated SaierNico Marine Switch board Maker: Zhenjiang Saiernico Electric Co. LTD Type : JYB-120 X 1/3 Gen. Power : 120 kW x 1 Volt : 450 V/230V, 60 Hz | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Emergency switch board to be serviced and all Meters to be callibrated | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
SaierNico Marine Switch board Maker: Zhenjiang Saiernico Electric Co. LTD Type : JYB-120 X 1/3 Gen. Power : 120 kW x 1 Volt : 450 V/230V, 60 Hz | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 006
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/006 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main engine control system and alarm panel of Kongsberg to be serviced and callibrated. | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
System : Kongsberg AutoChief 600, K-Chief600 | [5 empty] | Manufacturers' Representative
Maker: Kongsberg Maritime AS, Norway | [5 empty] | Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main engine control system and alarm panel of Kongsberg to be serviced and callibrated. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Kongsberg AutoChief 600, K-Chief600 | [5 empty] | Transportation outside yard
www.kongsberg.com | [5 empty] | Access work
Maker: Kongsberg Maritime AS, Norway | [5 empty] | Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 007
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/007 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main engine MAN B&W control system to be callibrated and serviced | [5 empty] | Flag Sate Representative
Software version : ME-ECS-SW-1312-3.4 |  |  |  |  | x | Owners Representative
Main Engine : MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Engine Control system sensors to be callibrated. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Software version : ME-ECS-SW-1312-3.4 | [5 empty] | Transportation internal
Main Engine : MAN-B&W 5S60ME-C8.2 (Tier II) | [5 empty] | Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 008
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON BREEZE
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD1/EL/008 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
All tanks sounding/tempreture sensors of Ballast Control System to be serviced, repaired and callibrated. Ballast Control System Maker : UTSUKI KEIKI CO. LTD, Yokohoma, Japan | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
All tanks sounding/tempreture sensors of Ballast Control System to be serviced, repaired and callibrated. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Transportation internal
Ballast Control System | [5 empty] | Transportation outside yard
Maker : UTSUKI KEIKI CO. LTD, Yokohoma, Japan | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 009
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD1/EL/009 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
ICCP System dry Dock routine to be carried out. Maker: K.C. LTD, Koria Web: www.iccp-mgps.com Email: kcind@iccp-mgps.com | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
[5 empty] | x | Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
ICCP System dry Dock routine to be carried out. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker: K.C. LTD, Koria | [5 empty] | Transportation internal
Web: www.iccp-mgps.com | [5 empty] | Transportation outside yard
Email: kcind@iccp-mgps.com | [5 empty] | Access work
Corrosion protection
K.C. LTD Ref No: K159751/B | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
K.C. LTD (Maker) should be notified 30 days prior to Dry dock and Daily Log sheets to be forwarded to K.C. LTD
Other details
Materials
Yard supply
[5 empty] | x | Owner’s supply
[5 empty] | x | Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 010
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD1/EL/010 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
MGPS System dry Dock routine to be carried out. Maker: K.C. LTD, Koria Web: www.iccp-mgps.com Email: kcind@iccp-mgps.com | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
[5 empty] | x | Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
MGPS System dry Dock routine to be carried out. | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker: K.C. LTD, Kora | [5 empty] | Transportation internal
Web: www.iccp-mgps.com | [5 empty] | Transportation outside yard
Email: kcind@iccp-mgps.com | [5 empty] | Access work
Corrosion protection
K.C. LTD Ref No: KM59752/B | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
Yard supply
[5 empty] | x | Owner’s supply
[5 empty] | x | Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 011
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CB/DD1/EL/011 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Load test of all Deck cranes Macgregor Crane Type: GLB3030-2/2430gr Four Cranes | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Macgregor Crane | [5 empty] | Transportation internal
Type: GLB3030-2/2430gr | [5 empty] | Transportation outside yard
Four Cranes | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 012
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/012 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Steering gear motors to be serviced and bearings to be replaced (2 motors) | [5 empty] | Flag Sate Representative
Maker : Higen Motors CO. LTD |  |  |  |  | x | Owners Representative
Model : 150HV1TH-YW | [5 empty] | Manufacturers' Representative
440V/60Hz, 37kW, 1770 rpm | [5 empty] | Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Steering gear motors to be serviced and bearings to be replaced | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Maker : Higen Motors CO. LTD | [5 empty] | Transportation internal
Model : 150HV1TH-YW |  |  |  |  | x | Transportation outside yard
440V/60Hz, 37kW, 1770 rpm | [5 empty] | Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 013
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/013 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
M/E Auxiliary blower motors to be serviced and replaced bearing Type : Y2E2 225M-2 Power 440V/54 kW Severy : JAD1501-02 Maker : HOYER www.hoyermotors.com | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
M/E Auxiliary Blowers to be serviced and motor bearings . | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Type : LCF6025 Power 440V/54 kW Severy : JAD1501-02 Maker : HOYER www.hoyermotors.com | [5 empty] | Transportation internal
[5 empty] | x | Transportation outside yard
Access work
Corrosion protection
Bearing DE 6312/C3 NDE 6312/C3 | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 014
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/014 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Low temprature cooling water system motors to be serviced and replaced bearing Type : M2QA225M4A Power 440V/45 kW Maker : ABB MARINE MOTORS | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Low temprature cooling water system motors to be serviced and replaced bearing | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Type : M2QA225M4A Power 440V/54 kW Maker : ABB MARINE MOTORS | [5 empty] | Transportation internal
[5 empty] | x | Transportation outside yard
Access work
Corrosion protection
Bearing DE 63132Z/C3 NDE 63132Z/C3 | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 015
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/015 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Fire and GS pump motors to be serviced and replaced bearing Type : M2QA250M2A Power 440V/55 kW Maker : ABB MARINE MOTORS | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Fire and GS pump motors to be serviced and replaced bearing | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Type : M2QA250M2A Power 440V/55 kW Maker : ABB MARINE MOTORS | [5 empty] | Transportation internal
[5 empty] | x | Transportation outside yard
Access work
Corrosion protection
Bearing DE 6314/C3 NDE 6314/C3 | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 016
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/016 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Bilge and GS pump motors to be serviced and replaced bearing Type : M2QA250M2A Power 440V/55 kW Maker : ABB MARINE MOTORS | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Bilge and GS pump motors to be serviced and replaced bearing | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Type : M2QA250M2A Power 440V/55 kW Maker : ABB MARINE MOTORS | [5 empty] | Transportation internal
[5 empty] | x | Transportation outside yard
Access work
Corrosion protection
Bearing DE 6314/C3 NDE 6314/C3 | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 017
CEYLON SHIPPING CORPORATION LTD+A1:J44+A1:J41
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/017 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Main Air Compressor motors to be serviced and replaced bearing Type : HMC2 280S-6 Power 440V/52.4 kW Maker : HOYER www.hoyermotors.com | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Main Air Compressor motors to be serviced and replaced bearing | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Type : HMC2 280S-6 Power 440V/52.4 kW Maker : HOYER www.hoyermotors.com | [5 empty] | Transportation internal
[5 empty] | x | Transportation outside yard
Access work
Corrosion protection
Bearing DE 6317/C3 NDE 6314/C3 | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 018
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/018 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Ballast pump motors to be serviced and replaced bearing Type : M2QA280M4A Power 440V/99 kW Maker : ABB MARINE MOTORS | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Ballast pump motors to be serviced and replaced bearing | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Type : M2QA280M4A Power 440V/55 kW Maker : ABB MARINE MOTORS | [5 empty] | Transportation internal
[5 empty] | x | Transportation outside yard
Access work
Corrosion protection
Bearing DE 6316/C3 NDE 6316/C3 | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 019
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/019 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
Class Representative
Sea Water Cooling pump motors to be serviced and replaced bearing Type : M2QA225S4A Power 440V/37 kW Maker : ABB MARINE MOTORS | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
'Sea Water Cooling pump motors to be serviced and replaced bearing | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
[5 empty] | x | Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Type : M2QA225S4A Power 440V/37 kW Maker : ABB MARINE MOTORS | [5 empty] | Transportation internal
[5 empty] | x | Transportation outside yard
Access work
Corrosion protection
Bearing DE 63132Z/C3 NDE 63132Z/C3 | [5 empty] | Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date

## EL 020
CEYLON SHIPPING CORPORATION LTD
SPECIFICATION OF REPAIRS (DOCKING)
Ship's Name: | CEYLON PRINCESS
ENGINE |  | VESSEL |  | OFFICE |  | YARD
|  | JOB No. | CP/DD1/EL/020 | JOB No. |  | JOB No.
Date : |  | Account Number
General description (Maker, Type, Rating, Weight, Volume, RPM, Voltage, No.etc.) |  |  |  |  | Inspection / Surveys
[5 empty] | x | Class Representative
Shore calibration of calibratores Maker: LR-Cal , Leitenberger GmbH, 72138 Kirchentellinsfurt, Germany. Model: LPP 40 | [5 empty] | Flag Sate Representative
[5 empty] | x | Owners Representative
Manufacturers' Representative
Underwriters
Others
Actual Job description |  |  |  |  | Yard work to be included
Calibratores calibrated and certificate to be issued | [5 empty] | Gas free certificate
Lighting
Ventilation
Cleaning before
Cleaning after
Details (Detailed Specification incl. Number, Size, Dimension, Material etc.) | [5 empty] | Staging
Crane service
Location: engine control room. | [5 empty] | Transportation internal
Transportation outside yard
Access work
Corrosion protection
Galvanizing
Paintwork (T/Up, Full Coat)
Pressure testing
[5 empty] | x | Function testing
Non-destructive test
Correction drawings
Location, material, access work, staging, other details & special reqmnts |  |  |  |  | Sub contract
Other details
Materials
[5 empty] | x | Yard supply
[5 empty] | x | Owner’s supply
Maker’s supply
Enclosures
Drawing
Prepared by |  |  | Approved by Manager SMT |  |  | Sketch
Photograph
Sample
Name, Rank, Signature & date |  |  | Name, Signature & date